## Dev
Braiins Development Schedule |  |  |  |  | All times in days | [13 empty] | Revised: | 2011-03-09 | Date of last addition of tasks or change in the estimated times.
[19 empty] | Last update: | 2011-03-09 | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [13 empty] | Start Date: | 2011-02-01 | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [13 empty] | Launch Date: | 2011-10-01 13:12 | Projected Ready to Launch Date
Postponed to post launch |  |  |  | Done: | Days completed
Could be postponed to post launch if necessary |  |  |  | To Do: | Days remaining to be done | [13 empty] | 1.1667 | 6 | Average effective development days per week
Ref | F | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
Admin Stuff
1 | * | Choose Name and buy domains | 1 |  | 1 | 0 | 2 |  | 2 | 0 |  |  |  |  | 3 | 0 | 3 | 3 | 0 | 2011-02-06 | Braiins chosen
1.1 |  | Set up Braiins Ltd UK | David To Do: 0; Charles Est.: 2; Charles Done: 1; Charles To Do: 1; Total Est.: 2; Total Var: 0; Total Done: 1; Total E + V: 2; Total To Do: 1
1.2 |  | Sort out ElanElan | David Est.: 2; David Done: 1; David To Do: 1; Charles To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 1; Total E + V: 2; Total To Do: 1
1.3 |  | Accounting, VAT, legal, banking etc admin stuff | David To Do: 0; Charles Est.: 5; Charles To Do: 5; Total Est.: 5; Total Var: 0; Total Done: 0; Total E + V: 5; Total To Do: 5
1.4 |  | HMRC Registered | David To Do: 0; Charles Est.: 2; Charles To Do: 2; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
1.5 |  | Other? | David Est.: 1; David To Do: 1; Charles Est.: 1; Charles To Do: 1; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
|  |  | 4 | 0 | 2 | 2 | 12 | 0 | 3 | 9 | 0 | 0 | 0 | 0 | 16 | 0 | 5 | 16 | 11
Project
2 | * | Initial Plans | 2 |  | 2 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 3 | 0 | 3 | 3 | 0 | 2011-02-03 | Main site plus Braiins Desktop
2.1 | * | Tools Selection | David Est.: 6; David Done: 6; David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 6; Total Var: 0; Total Done: 6; Total E + V: 6; Total To Do: 0 | 2011-02-27 | Xhtml, JavaScript, PHP, MySQL, jQuery, jDesktop, SlickGrid, WordPress, UniServer + various other jQuery plugins
2.2 | * | Initial Database design | David Est.: 2; David Done: 2; David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 2; Total E + V: 2; Total To Do: 0 | 2011-02-14
2.3 |  | Choose Payment Processing Service(s) | David Est.: 1; David To Do: 1; Charles Est.: 3; Charles To Do: 3; Others To Do: 0; Total Est.: 4; Total Var: 0; Total Done: 0; Total E + V: 4; Total To Do: 4
2.4 |  | Choose Hosting | David Est.: 1; David To Do: 1; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
|  |  | 12 | 0 | 10 | 2 | 5 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 17 | 0 | 11 | 17 | 6
Main Braiins.com Site
3 | * | Initial framework up | 6 |  | 6 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 7 | 0 | 7 | 7 | 0 | 2011-02-14
3.1 |  | Logo, favicon, & colours | 2 |  |  | 2 | 1 |  |  | 1 | 3 |  |  | 3 | 6 | 0 | 0 | 6 | 6 |  | Via Freelancer.com?
3.2 |  | Home Page | David Est.: 3; David To Do: 3; Charles Est.: 3; Charles To Do: 3; Others To Do: 0; Total Est.: 6; Total Var: 0; Total Done: 0; Total E + V: 6; Total To Do: 6 |  | Strap line, copy, images + slide show or video?
3.3 |  | Free Trial | David Est.: 0.2; David To Do: 0.2; Charles Est.: 0.2; Charles To Do: 0.2; Others To Do: 0; Total Est.: 0.4; Total Var: 0; Total Done: 0; Total E + V: 0.4; Total To Do: 0.4 |  | Small task as currently envisaged
3.4 |  | Registration | 4 |  | 3 | 1 | 2 |  | 2 | 0 |  |  |  | 0 | 6 | 0 | 5 | 6 | 1 |  | Terms of Service to be updated once task 3.10 is final. Guarantee to be agreed.
3.5 |  | Info: Features & Benefits | David Est.: 1; David To Do: 1; Charles Est.: 5; Charles To Do: 5; Others To Do: 0; Total Est.: 6; Total Var: 0; Total Done: 0; Total E + V: 6; Total To Do: 6 |  | Charles to write. Incl BDT images as per current Tari page?
3.6 |  | Info: Prices | David Est.: 0.5; David To Do: 0.5; Charles Est.: 3; Charles To Do: 3; Others To Do: 0; Total Est.: 3.5; Total Var: 0; Total Done: 0; Total E + V: 3.5; Total To Do: 3.5 |  | Charles to research and write
3.7 |  | Info: FAQs | David Est.: 0.5; David To Do: 0.5; Charles Est.: 2; Charles To Do: 2; Others To Do: 0; Total Est.: 2.5; Total Var: 0; Total Done: 0; Total E + V: 2.5; Total To Do: 2.5 |  | Charles to write
3.8 |  | Info: About Us | 1 |  | 0.5 | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 0 | 1.5 | 0 | 0.5 | 1.5 | 1 |  | Pic and copy due from Charles
3.9 |  | Info: Policies | David Est.: 1; David To Do: 1; Charles Est.: 2; Charles To Do: 2; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3 |  | David to revise with check by Charles
3.1 |  | Info: Terms | David Est.: 0.5; David To Do: 0.5; Charles Est.: 2; Charles To Do: 2; Others To Do: 0; Total Est.: 2.5; Total Var: 0; Total Done: 0; Total E + V: 2.5; Total To Do: 2.5 |  | Charles to revise. Legal opinion necessary?
3.11 | * | Sitemap | David Est.: 1; David Done: 1; David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 1; Total E + V: 1; Total To Do: 0
3.12 |  | Contact Us | 1 |  | 0.5 | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 0 | 1.5 | 0 | 0.5 | 1.5 | 1
3.13 |  | Change from cookies to local storage use | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
3.14 |  | Add browser version warnings | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
3.15 |  | Add Testimonials page | David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 0; Total Var: 0; Total Done: 0; Total E + V: 0; Total To Do: 0
3.16 |  | Misc | David Est.: 3; David To Do: 3; Charles To Do: 0; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3
|  |  | 27.7 | 0 | 11 | 16.7 | 22.2 | 0 | 3 | 19.2 | 3 | 0 | 0 | 3 | 52.9 | 0 | 14 | 52.9 | 38.9
Ref | F | Task | David Est.: David; Charles Est.: Charles; Others Est.: Others; Total Est.: Total | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
BDT - Braiins DeskTop
4 | * | Initial framework up incl Close | David Est.: 4; David Done: 4; David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 4; Total Var: 0; Total Done: 4; Total E + V: 4; Total To Do: 0 | 2011-02-27
4.1 |  | Actions: Logout | David Est.: 0.2; David To Do: 0.2; Charles To Do: 0; Others To Do: 0; Total Est.: 0.2; Total Var: 0; Total Done: 0; Total E + V: 0.2; Total To Do: 0.2
4.2 |  | Actions: Fullscreen | David Est.: 0.5; David To Do: 0.5; Charles To Do: 0; Others To Do: 0; Total Est.: 0.5; Total Var: 0; Total Done: 0; Total E + V: 0.5; Total To Do: 0.5 | 2008-06-17 | A trivial task!
4.3 | * | Actions: Minimise all open windows | David Est.: 0.1; David Done: 0.1; David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 0.1; Total Var: 0; Total Done: 0.1; Total E + V: 0.1; Total To Do: 0
4.4 |  | Actions: Change Entity | David Est.: 0.5; David To Do: 0.5; Charles To Do: 0; Others To Do: 0; Total Est.: 0.5; Total Var: 0; Total Done: 0; Total E + V: 0.5; Total To Do: 0.5
4.5 |  | Accounts: Set Current Year | David Est.: 0.5; David To Do: 0.5; Charles To Do: 0; Others To Do: 0; Total Est.: 0.5; Total Var: 0; Total Done: 0; Total E + V: 0.5; Total To Do: 0.5 |  | When credits are charged
4.6 |  | Accounts: Upload Data | 2 |  |  | 2 | 28 |  | 11 | 17 |  |  |  | 0 | 30 | 0 | 11 | 30 | 19 |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
4.7 |  | Accounts: Edit Data | David Est.: 21; David To Do: 21; Charles Est.: 10; Charles To Do: 10; Others To Do: 0; Total Est.: 31; Total Var: 0; Total Done: 0; Total E + V: 31; Total To Do: 31 |  | Includes taxonomy stuff and prompted user tagging of text where appropriate/necessary
4.8 |  | Accounts: Generate Accounts | 28 |  |  | 28 | 60 |  | 14 | 46 |  |  |  | 0 | 88 | 0 | 14 | 88 | 74 |  | Report generator by D plus formats by C incl taxonomy info
4.1 |  | Accounts: Download Accounts | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
4.11 |  | Accounts: Export Data | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
4.12 |  | Accounts: Tagging Reports | David Est.: 5; David To Do: 5; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 6; Total Var: 0; Total Done: 0; Total E + V: 6; Total To Do: 6
4.13 |  | Entities: Change Entity | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
4.14 |  | Entities: New Entity | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
4.15 |  | Entities: Edit, Reset, Delete Entity | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
4.16 |  | Entities: Entities List | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
4.17 |  | Interaction: Messages | David Est.: 5; David To Do: 5; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 6; Total Var: 0; Total Done: 0; Total E + V: 6; Total To Do: 6
4.18 |  | Interaction: Support | David Est.: 2; David To Do: 2; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3 |  | Based on task 4.17
4.19 |  | Interaction: Documentation | David Est.: 2; David To Do: 2; Charles Est.: 7; Charles To Do: 7; Others To Do: 0; Total Est.: 9; Total Var: 0; Total Done: 0; Total E + V: 9; Total To Do: 9 |  | Charles to write. Initial version only
4.2 |  | Interaction: Training | David Est.: 2; David To Do: 2; Charles Est.: 7; Charles To Do: 7; Others To Do: 0; Total Est.: 9; Total Var: 0; Total Done: 0; Total E + V: 9; Total To Do: 9 |  | Charles to write. Initial version only
4.21 |  | Preferences: Headings | 6 |  | 5 | 1 | 1 |  |  | 1 |  |  |  | 0 | 7 | 0 | 5 | 7 | 2 |  | Most of the time was choosing and learning tools time.
4.22 |  | Preferences; Layout Options | David Est.: 5; David To Do: 5; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 6; Total Var: 0; Total Done: 0; Total E + V: 6; Total To Do: 6
4.23 |  | Admin: Agent Details (Account) | David Est.: 2; David To Do: 2; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3
4.24 |  | Admin: Administrator | David Est.: 1; David To Do: 1; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
4.25 |  | Admin: Staff | David Est.: 2; David To Do: 2; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3
4.26 |  | Admin: Credits | David Est.: 5; David To Do: 5; Charles Est.: 3; Charles To Do: 3; Others To Do: 0; Total Est.: 8; Total Var: 0; Total Done: 0; Total E + V: 8; Total To Do: 8 |  | Includes payment processing interaction
4.27 |  | Admin: Download Export Format | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1 |  | Charles' work for this is in task 4.6
4.28 |  | Admin: Admin Reports | David Est.: 3; David To Do: 3; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 4; Total Var: 0; Total Done: 0; Total E + V: 4; Total To Do: 4
4.29 |  | jDesktop tidying up | David Est.: 5; David To Do: 5; Charles To Do: 0; Others To Do: 0; Total Est.: 5; Total Var: 0; Total Done: 0; Total E + V: 5; Total To Do: 5
4.3 |  | Misc | David Est.: 5; David To Do: 5; Charles Est.: 3; Charles To Do: 3; Others To Do: 0; Total Est.: 8; Total Var: 0; Total Done: 0; Total E + V: 8; Total To Do: 8
|  |  | 116.8 | 0 | 9.1 | 107.7 | 127 | 0 | 25 | 102 | 0 | 0 | 0 | 0 | 243.8 | 0 | 34.1 | 243.8 | 209.7
Ref | F | Task | David Est.: David; Charles Est.: Charles; Others Est.: Others; Total Est.: Total | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
Blog
5 |  | Set it up with logo etc @ blog.braiins.com | David Est.: 4; David To Do: 4; Charles To Do: 0; Others To Do: 0; Total Est.: 4; Total Var: 0; Total Done: 0; Total E + V: 4; Total To Do: 4
5.1 |  | Enable Braiins Newsletter sign up | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2 |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
5.2 |  | Write and post launch blogs | David Est.: 1; David To Do: 1; Charles Est.: 2; Charles To Do: 2; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3
5.3 |  | Write and post blogs post launch | David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 0; Total Var: 0; Total Done: 0; Total E + V: 0; Total To Do: 0 |  | Ongoing after launch
|  |  | 7 | 0 | 0 | 7 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 9
Admin
6 |  | Set up an Admin Desktop @ admin.braiins.com | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2 |  | Based on BDT
6.1 |  | Edit people esp password | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1 |  | Based on task 4.25
6.2 |  | Support Message System | David Est.: 1; David To Do: 1; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
6.3 |  | Credits Journals | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
6.4 |  | Report: Agents & Entities | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
6.5 |  | Report: Credits i.e. Money Stuff | David Est.: 0.5; David To Do: 0.5; Charles To Do: 0; Others To Do: 0; Total Est.: 0.5; Total Var: 0; Total Done: 0; Total E + V: 0.5; Total To Do: 0.5
6.6 |  | Report: Site Usage and Tracking Stuff | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1
6.7 |  | Housekeeping (End of Day) cron task | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
6.8 |  | Down for maintenance page | David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 0; Total Var: 0; Total Done: 0; Total E + V: 0; Total To Do: 0
|  |  | 9.5 | 0 | 0 | 9.5 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10.5 | 0 | 0 | 10.5 | 10.5
Marketing
7 |  | Setup Google Analytics & add code to main pages | David Est.: 0.5; David To Do: 0.5; Charles To Do: 0; Others To Do: 0; Total Est.: 0.5; Total Var: 0; Total Done: 0; Total E + V: 0.5; Total To Do: 0.5
7.1 |  | Submit to SEs | David Est.: 0.5; David To Do: 0.5; Charles To Do: 0; Others To Do: 0; Total Est.: 0.5; Total Var: 0; Total Done: 0; Total E + V: 0.5; Total To Do: 0.5
7.2 |  | Issue Press Releases | David Est.: 0.5; David To Do: 0.5; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 1.5; Total Var: 0; Total Done: 0; Total E + V: 1.5; Total To Do: 1.5
7.3 |  | Contact AccMan, AW, AA etc | David Est.: 0.5; David To Do: 0.5; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 1.5; Total Var: 0; Total Done: 0; Total E + V: 1.5; Total To Do: 1.5
7.4 |  | More, much more…. | 2 |  |  | 2 | 10 |  |  | 10 | 10 |  |  | 10 | 22 | 0 | 0 | 22 | 22
|  |  | 4 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | 10 | 0 | 0 | 10 | 26 | 0 | 0 | 26 | 26
Launch Preparation
8 |  | Test and fix, test and fix incl cross browser issues | David Est.: 14; David To Do: 14; Charles Est.: 7; Charles To Do: 7; Others To Do: 0; Total Est.: 21; Total Var: 0; Total Done: 0; Total E + V: 21; Total To Do: 21
8.1 |  | Get HMRC approval | David Est.: 2; David To Do: 2; Charles Est.: 2; Charles To Do: 2; Others To Do: 0; Total Est.: 4; Total Var: 0; Total Done: 0; Total E + V: 4; Total To Do: 4
8.2 |  | Set up deployment server | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1 |  | Incl gzip
8.3 |  | Tidy & minimise JS, CSS, HTML + optimise | David Est.: 3; David To Do: 3; Charles To Do: 0; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3
8.4 |  | Get SSL certificate and get SSL working | David Est.: 2; David To Do: 2; Charles Est.: 1; Charles To Do: 1; Others To Do: 0; Total Est.: 3; Total Var: 0; Total Done: 0; Total E + V: 3; Total To Do: 3
8.5 |  | Remove authorisation login | David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 0; Total Var: 0; Total Done: 0; Total E + V: 0; Total To Do: 0 |  | 5 minutes!
8.6 |  | Finalise payment processing | David Est.: 2; David To Do: 2; Charles Est.: 2; Charles To Do: 2; Others To Do: 0; Total Est.: 4; Total Var: 0; Total Done: 0; Total E + V: 4; Total To Do: 4
8.7 |  | Misc | David Est.: 5; David To Do: 5; Charles Est.: 5; Charles To Do: 5; Others To Do: 0; Total Est.: 10; Total Var: 0; Total Done: 0; Total E + V: 10; Total To Do: 10
|  |  | 29 | 0 | 0 | 29 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 46 | 46
| 8 | Totals and Ready to LAUNCH Day | 210 | 0 | 32.1 | 177.9 | 198.2 | 0 | 32 | 166.2 | 13 | 0 | 0 | 13 | 421.2 | 0 | 64.1 | 421.2 | 357.1 | 2011-10-01 13:12 | Based on djh "To Do" days
|  | Total days incl Var, % done | 210 | 15.29% |  | 0 | 198.2 | 16.15% |  | 0 | 13 | 0% |  | 0 | 421.2 | 15.22% |  |  | 0
|  | Available days (effective days) | David Done: 31.7143; Charles Done: 31.7143
|  | Check - should be approx 0 | David Done: -0.38571; Charles Done: -0.28571
Ref | F | Task | David Est.: David; Charles Est.: Charles; Others Est.: Others; Total Est.: Total | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
Post Launch
9 |  | Add Testimonials page
9.1 |  | Write and post blogs post launch
9.2 |  | Down for maintenance page
Niceties Not Essential for Launch
10 |  | Add effects to main site menu | David Est.: 2; David To Do: 2; Charles To Do: 0; Others To Do: 0; Total Est.: 2; Total Var: 0; Total Done: 0; Total E + V: 2; Total To Do: 2
10.1 |  | Add a password strength bar to registration | David Est.: 1; David To Do: 1; Charles To Do: 0; Others To Do: 0; Total Est.: 1; Total Var: 0; Total Done: 0; Total E + V: 1; Total To Do: 1 |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
|  |  | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
|  |  | David To Do: 0; Charles To Do: 0; Others To Do: 0; Total Est.: 0; Total Var: 0; Total Done: 0; Total E + V: 0; Total To Do: 0 |  | Ongoing after launch
Notes:
Projected Ready for Launch Date at time of issue
Document Issue History | [19 empty] | 2011-10-01
09 Mar 11 First issue
Formulas:
Est/Act Date = U2+[To Do]*T6-1

## MAS
Maketing Automation System Deveopment Tasks from the MAS Spec as at 29.03.04
Task | Task | Estimated Days | Days Done | Variation | Days Left
#
Tracking
Preparation
T1 | Create the MAS database, and add the new DB Tables | 1 | 1 |  | 0 | 1 | 30.03.04 2 -> 1
T2 | ASCodes (Associates Scheme Codes) is to be generalised to TCodes, and ASLinkClicks (Associates Scheme Link Clicks) is to be deleted, with Visits expanded as required to handle the previous ASLinkClicks functions. | 1 | 2 | 1 | 0 | 1 | 30.03.04 2 -> 1
T3 | Write a custom 404 page to direct visitors arriving via a tracking link to the tracking link processing page, or configure Apache via the mod_rewrite module to do the job. [AliasMatch used.] | 3 | 1 | -2 | 0
T4 | Generalise the current Associates Scheme tracking link processing script ASLink.inc and rename it PreProc.php. Move the attempted matching for no cookie arrivals back up into SessionsStart() in the process. See sections 3.2.5.2 Visitor arriving via a tracking link and 3.2.5.3 Visitor who does not arrive via a tracking link. [All handled via index.php and SessionStart() thanks to AliasMatch.] | 2 | 1 | -1 | 0
T5 | Make Join set the Marketing Activity for a new Member joined by an existing Member to ‘Joined by Member’. See 3.2.5.4 Member Joined by Another Member | 1 | 0.2 | -0.8 | 0
Session Handling Changes
T6 | Change ASLCId in the Sessions and Visits tables to TFVisitsId and similarly change the global sessions variable $ASLCId to $TFVisitsId everywhere, plus associated comments. | 0.4 | 1 | 0.6 | 0 | 0.6 | 30.03.04 1 -> 0.4
T7 | Make NewSession() include the TFVistsId | 0.2 | 0.2 |  | 0
T8 | Add a url field to the Visits table [Referrer] | 0.2 | 0.2 |  | 0
| ‘Traditional’ Web Site Tracking |  |  |  | 0
T9 | Install phpOpenTracker |  |  |  | 0 | 2 | 30.03.04 -> post launch
T10 | Integrate phpOpenTracker with the LeLotto site and MAS |  |  |  | 0 | 5 | 30.03.04 -> post launch
T11 | Select, customise and extending reports and make them available via MAS |  |  |  | 0 | 5 | 30.03.04 -> post launch
Marketing Campaigns
T12 | Add/Edit/Delete Marketing Campaigns. CPM or CPC changes must include an effective date. | 2 | 2 |  | 0
Marketing Activities and Related Tracking
T13 | Add/Edit/Delete Marketing Activities | 2 | 2 |  | 0 | 2 | 30.03.04 4 -> 2
T14 | Capture the required data as a by product of the operation of LeLotto. (Extend and adjust the current Associates Scheme work.) | 4 | 1 |  | 3
T15 | Extend Login (MemWrk.php) to check no cookie tracking load cases and retrospectively adjust the visits case if it becomes apparent that TPreProc.php made the wrong choice. See 3.2.5 The Tracking Process | 2 | 0.25 | -1.75 | 0
T16 | Class to generate a tracking code for use by the manual or automatic routines. (Modify class written for Associates Scheme.) | 0.5 | 0.5 |  | 0 | 0.5 | 30.03.04 1 -> 0.5
T17 | Create tracking code for the cases where such as PR where code generation is not automatic | 0.5 | 0.5 |  | 0 | 0.5 | 30.03.04 1 -> 0.5
T18 | Generation and posting of MA Transactions as part of End of Day processing. | 2 |  |  | 2
T19 | Manual entry and posting of MA transactions | 2 |  |  | 2
T20 | Add/Edit/Delete Tracking Urls – the TUrls table – which must integrate with the Associates Scheme re a default referrer url and tracking code. | 2 |  |  | 2
T21 | Link in a forum system for Marketing/Campaign note taking purposes |  |  |  | 0 | 5 | 30.03.04 -> post launch. Use a wiki?
Search Engine
T22 | Add search engine detection to to the current SessionStart() function in SessionMax.inc, possibly via the CReferrer class, with the results to be recorded in the MAS table SEVisits. This is to be done for all visits, regardless of whether they include a tracking code or not. | 3 | 1 | -2 | 0
Associates Scheme
T23 | Devise a process to link general tracking information for Associate Scheme visitors to the additional Associate Scheme specific tables, based on the Marketing Activity type for the Associate Scheme | 1 |  |  | 1
T24 | Change the current Associates Scheme code creation to use the new general routine | 1 | 1 |  | 0
T25 | Add new DB tables for Associates and ASGrades | 1 |  |  | 1
T26 | Add a procedure to Control Panel for signing up as an Associate | 2 |  |  | 2
T27 | Add a procedure to Control Panel for resigning as an Associate. This will require some process to handle reclassifying the associate’s associatees, and accounting for this in reporting | 2 |  |  | 2
T28 | Add a default referrer url and default tracking code re the TUrls table for the ‘no tracking link no cookie’ arrivals case | 1 |  |  | 1
T29 | Prevent deletion of a member who is an Associate | 0.2 |  |  | 0.2
T30 | Add a procedure for recording whether an Associate is a member of the Affiliate Showcase Scheme, and if so, at what level i.e. Free, Pro, or Executive | 1 |  |  | 1
T31 | Add an admin procedure to Add/Edit the ASGrades table, and to manually set grades re JV negotiations | 2 |  |  | 2
T32 | Extend End of Day to perform the grade related processing | 2 |  |  | 2
T33 | Check associatee status for Syndicates | 1 | 0.5 | -0.5 | 0
T34 | Provide a means of resolving tracking disputes i.e. a claim from Associate A that Member M should have been identified as an Associatee of Associate A. This will mean looking through the Visits records to see if a mistake could have been made. See 3.2.5 The Tracking Process |  |  |  | 0 | 4 | 30.03.04 -> post launch
Emails – Own Lists
T35 | Integration of email specific requirements into the tracking system | 4 |  |  | 4
T36 | Integration with the mailing system |  |  |  | 0 | 2 | 30.03.04 double counted
T37 | Module to serve tracking images to html emails and record the hits | 2 |  |  | 2
T38 | Unsubscribe link operation | 2 |  |  | 2
Ezines
T39 | Integration of the ezine specific requirements into the tracking system |  |  |  | 0 | 2 | 30.03.04 done as part of T35
T40 | Integration with the mailing system |  |  |  | 0 | 2 | 30.03.04 double counted
T41 | A ‘LeLotto News’ page for non-member subscribers, where they can change their html/text choice, their email address, name etc, and also unsubscribe | 2 |  |  | 2
T42 | A ‘double opt in’ process for ezine subscriptions, in two forms, one for Members and another for all other subscribers | 2 |  |  | 2
T43 | Unsubscribe link operation |  |  |  | 0 | 1 | 30.03.04 done as part of T38
T44 | Add a ‘Subscribe to Ezine’ link to the bottom right of the site, which brings up a subscribe form, which could also offer other things e.g. ebook, and ask the ‘How did you hear about LeLotto please?’ question in the unknown source case. | 2 |  |  | 2
T45 | Add a ‘Subscribe to Ezine’ exit popup for visitors who haven’t subscribed or joined, with options as for the above item. | 1 |  |  | 1 | 1 | 30.03.04 2 -> 1
Ebooks
T46 | Integration of the ebook specific requirements into the tracking system |  |  |  | 0 | 1 | 30.03.04 done as part of T35
T47 | Download module which generates an MTrans transaction for the download | 2 |  |  | 2
T48 | Add an optional ‘Subscribe to Ezine’ form at the point of download, and ask the ‘How did you hear about LeLotto please?’ question in the unknown source case. | 1 |  |  | 1 | 1 | 30.03.04 2 -> 1
Advertisements Online
T49 | Integration of the ad specific requirements into the tracking system |  |  |  | 0 | 2 | 30.03.04 done as part of T35
T50 | Enter (post) Impression, and Cost Transactions | 2 |  |  | 2
T51 | Generation and posting of Cost Transactions as part of End of Day processing | 2 |  |  | 2
List Building System
L1 | Add/Edit/Delete LLists | 2 |  |  | 2
L2 | Add ‘built-in’ list knowledge to the list system incl capture of the required data as a by product of the operation of LeLotto | 3 |  |  | 3 | 1 | 30.03.04 4 -> 3
L3 | Add/Edit/Copy/Move/Delete List People, with smart ways to find the required person. [A People module has been written but that will need to be extended and enhanced.] | 2 | 5 | 3 | 0
L4 | Integrate the above with the Help System, when that is written, so that Customer Service staff will have full information available about the person they are talking/chatting with, and can re-subscribe them to LeLotto News, for example, if they have unsubscribed, but are now ready to resume receipt |  |  |  | 0 | 2 | 30.03.04 -> post launch
L5 | Add/Edit/Delete Organisations, with smart ways to find the required organisation. [An Organisations module has been written but that will need to be extended and enhanced.] | 1 | 2 | 1 | 0
L6 | Add/Edit/Delete Relationships. [A Relationships module has been written but that needs to be moved to POrgs, and some enhancement may be required.] | 1 | 1 |  | 0
L7 | Import a list, with flexible mapping of the other list’s fields to ours, even potentially including logic |  |  |  | 0 | 3 | 30.03.04 do manually as required
L8 | Maintenance utilities for the People table to generate the alternative names form from what is available; and to flag potential duplicates for a human decision. |  |  |  | 0 | 3 | 30.03.04 -> post launch
L9 | Make Individual, Syndicate Master, and Internet Café member joins ‘double opt in’ by not taking full effect until the Member makes a deposit | 1 |  |  | 1 | 1 | 30.03.04 2 -> 1
Mailing System
User Initiated Mailings
M1 | Add/Edit/Delete Mailings. Editing is not to be allowed once a mailing has been sent. A previous mailing can be used as a template for a new one. Filtering options are to be dynamic according to the list type or types chosen. Directories and file name selections should also be live i.e. selected from a select box | 5 |  |  | 5 | 2 | 30.03.04 7 -> 5
M2 | Process to run a test mailing | 1 |  |  | 1
M3 | Run a mailing step 1: process the list or lists, applying the filters, and eliminating duplicates | 1 |  |  | 1
M4 | Run a mailing step 2: advise the number of emails to be sent, and allow Abort before actual mailing starts, or the wait for a time delayed mailing, starts | 1 |  |  | 1
M5 | Run a mailing step 3: send the mailing, with progress feedback phpMailer can help with this. See php¦architect December 2003 "Mailing List Management with PHP Mailer" and http://phpmailer.sourceforge.net/. Allow for the mailing to be aborted. | 4 |  |  | 4 | 2 | 30.03.04 6 -> 4
M6 | Run time delayed mailings at the set time, using the Automatic Mail handler |  |  |  | 0 | 1 | 30.03.04 -> post launch
M7 | Provide a means of attaching to a time delayed mailing, either before or after it has started sending, to see its progress, and potentially to abort it |  |  |  | 0 | 1 | 30.03.04 -> post launch
M8 | Integrate updating of the MailSent table for failure reports received from the SMTP server | 2 |  |  | 2
M9 | Change LeLotto email sending to use the same, or a similar process, to that devised for bulk mailing via direct connection to the SMTP server, rather than one at a time via Mail(), so that there is less email sending overhead in the online processes. (Play.php takes longer to send the confirming email, than it does to process the entries.) | 3 |  |  | 3
Automatic Mail
M10 | Add/Edit/Delete Auto Emails. Directories and file name selections should be live i.e. selected from a select box. Adding or editing auto-responder emails must write appropriate program code as discussed in the AutoEmails Table Notes | 5 |  |  | 5 | 2 | 30.03.04 7 -> 5
M11 | Process to check AutoMailIP and initiate time delayed mailings, a triggered event mailing, or send series mails, all at the set times, and perform housework as necessary | 2 |  |  | 2
Incoming Mail
M12 | Choose and install an anti-virus/worm/trojan package for the LeLotto mail server |  |  |  | 0 | 5 | 30.03.04 -> sys admin person
M13 | Choose, install, and configure a spam filtering package |  |  |  | 0 | 5 | 30.03.04 -> sys admin person
M14 | Write an incoming mail detection and processing module to perform the operations listed above, and hook it into Postfix email processing | 7 |  |  | 7
Reporting System
R1 | Investigate phpOpenTracker’s reporting facilities and decide how best to make use of them, and to integrate them with MAS reporting |  |  |  | 0 | 2 | 30.03.04 -> post launch
R2 | Devise a Menu scheme | 1 |  |  | 1 | 1 | 30.03.04 2 -> 1
R3 | Add/Edit/Delete Reports | 1 |  |  | 1 | 1 | 30.03.04 2 -> 1
R4 | Report design system, which initially may be a formatting language for use with text files |  |  |  | 0 | 12 | 30.03.04 Cut out in favour of fixed reports
R5 | Front end to display the menu of available reports, and to accept the filtering and range inputs | 6 |  |  | 6
R6 | Report execute/run time system |  |  |  | 0 | 12 | 30.03.04 Cut out in favour of fixed reports
R7 | Link to a graphics package to allow graphical outputs |  |  |  | 0 | 7 | 30.03.04 Cut out in favour of fixed reports
R8 | Csv output option to allow transfer of report results to other packages |  |  |  | 0 | 3 | 30.03.04 -> post launch
R9 | Set of standard reports | 4 | 8 | 8 | 4
R10 | Report to give the history of any master table field with edits recorded via the change recording system | 1 |  |  | 1
Management and Control
Management
A1 | Add/Edit/Delete DBs incl creating All and setting up DBs | 1 | 1 |  | 0
A2 | Add/Edit/Delete Tables incl importing current tables | 1 | 1.5 | 0.5 | 0
A3 | Add/Edit/Delete TableDefs incl importing current table defs | 2 | 1 |  | 1
A4 | Develop a general class or function for recording changes to data held in the MAS database that are not the result of ‘posting’ a transaction i.e. i.e. all user initiated edits. | 2 | 1 | -1 | 0 | 1 | 30.03.04 3 -> 2
A5 | Procedure to change the running tables to match the definitions i.e. insert/drop/change columns and indices as required | 2 |  |  | 2
A6 | End of Year process to ‘Balance Forward’ all Master tables which have values updated by transactions, incl Marketing Activities |  |  |  | 0 | 2 | 30.03.04 -> post launch
A7 | Backup | 2 |  |  | 2
A8 | Restore | 2 |  |  | 2
A9 | Archive |  |  |  | 0 | 2 | 30.03.04 -> post launch
| Control |  |  |  | 0
A10 | Add/Edit/Delete Users, including setting of rights. Only be highest access level person! | 2 | 2 |  | 0
A11 | Implement an Admin/MAS login and session system distinct from the LeLotto one, though it can be based on the LeLotto one | 2 | 2 |  | 0
A12 | Implement the access control system | 2 | 2 |  | 0
Current Site and General Work
C1 | Create a new POrgs database, and transfer the current People and Orgs tables in the LInfo and Site DBs to POrgs | 1 | 1 |  | 0
C2 | Delete the MemStats fields as per the discussion in section 3.2.5.5 Data Gathering: | 1 | 0.5 | -0.5 | 0
C3 | Apply the Master table change recording system to already operating Master tables e.g. Members. | 3 | 3 |  | 0
C4 | Add a field to Join for ‘How did you hear about LeLotto’ if the source is unknown at Join time. | 1 |  |  | 1
C5 | Rework the current Orgs, Linfo, Charities, and Site admin ops as per the new People standard | 4 | 10 | 6 | 0
Total Estimated Days |  | 147 | 56.35 | 10.55 | 101.2 | 109.6