## Dev
Braiins Development Schedule |  |  |  |  | All times in days | [13 empty] | Revised: | 2011-03-09 | Date of last addition of tasks or change in the estimated times.
[19 empty] | Last update: | 2011-03-09 | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [13 empty] | Start Date: | 2011-02-01 | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [13 empty] | Launch Date: | 2011-10-01 13:12 | Projected Ready to Launch Date
Postponed to post launch |  |  |  | Done: | Days completed
Could be postponed to post launch if necessary |  |  |  | To Do: | Days remaining to be done | [13 empty] | 1.1667 | 6 | Average effective development days per week
Ref | F | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
Admin Stuff
1 | * | Choose Name and buy domains | 1 |  | 1 | 0 | 2 |  | 2 | 0 |  |  |  |  | 3 | 0 | 3 | 3 | 0 | 2011-02-06 | Braiins chosen
1.1 |  | Set up Braiins Ltd UK |  |  |  | 0 | 2 |  | 1 | 1 |  |  |  |  | 2 | 0 | 1 | 2 | 1
1.2 |  | Sort out ElanElan | 2 |  | 1 | 1 |  |  |  | 0 |  |  |  |  | 2 | 0 | 1 | 2 | 1
1.3 |  | Accounting, VAT, legal, banking etc admin stuff |  |  |  | 0 | 5 |  |  | 5 |  |  |  |  | 5 | 0 | 0 | 5 | 5
1.4 |  | HMRC Registered |  |  |  | 0 | 2 |  |  | 2 |  |  |  |  | 2 | 0 | 0 | 2 | 2
1.5 |  | Other? | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 2 | 0 | 0 | 2 | 2
|  |  | 4 | 0 | 2 | 2 | 12 | 0 | 3 | 9 | 0 | 0 | 0 | 0 | 16 | 0 | 5 | 16 | 11
Project
2 | * | Initial Plans | 2 |  | 2 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 3 | 0 | 3 | 3 | 0 | 2011-02-03 | Main site plus Braiins Desktop
2.1 | * | Tools Selection | 6 |  | 6 | 0 |  |  |  | 0 |  |  |  | 0 | 6 | 0 | 6 | 6 | 0 | 2011-02-27 | Xhtml, JavaScript, PHP, MySQL, jQuery, jDesktop, SlickGrid, WordPress, UniServer + various other jQuery plugins
2.2 | * | Initial Database design | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 2 | 0 | 2011-02-14
2.3 |  | Choose Payment Processing Service(s) | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4 | 4
2.4 |  | Choose Hosting | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
|  |  | 12 | 0 | 10 | 2 | 5 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 17 | 0 | 11 | 17 | 6
Main Braiins.com Site
3 | * | Initial framework up | 6 |  | 6 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 7 | 0 | 7 | 7 | 0 | 2011-02-14
3.1 |  | Logo, favicon, & colours | 2 |  |  | 2 | 1 |  |  | 1 | 3 |  |  | 3 | 6 | 0 | 0 | 6 | 6 |  | Via Freelancer.com?
3.2 |  | Home Page | 3 |  |  | 3 | 3 |  |  | 3 |  |  |  | 0 | 6 | 0 | 0 | 6 | 6 |  | Strap line, copy, images + slide show or video?
3.3 |  | Free Trial | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 |  |  |  | 0 | 0.4 | 0 | 0 | 0.4 | 0.4 |  | Small task as currently envisaged
3.4 |  | Registration | 4 |  | 3 | 1 | 2 |  | 2 | 0 |  |  |  | 0 | 6 | 0 | 5 | 6 | 1 |  | Terms of Service to be updated once task 3.10 is final. Guarantee to be agreed.
3.5 |  | Info: Features & Benefits | 1 |  |  | 1 | 5 |  |  | 5 |  |  |  | 0 | 6 | 0 | 0 | 6 | 6 |  | Charles to write. Incl BDT images as per current Tari page?
3.6 |  | Info: Prices | 0.5 |  |  | 0.5 | 3 |  |  | 3 |  |  |  | 0 | 3.5 | 0 | 0 | 3.5 | 3.5 |  | Charles to research and write
3.7 |  | Info: FAQs | 0.5 |  |  | 0.5 | 2 |  |  | 2 |  |  |  | 0 | 2.5 | 0 | 0 | 2.5 | 2.5 |  | Charles to write
3.8 |  | Info: About Us | 1 |  | 0.5 | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 0 | 1.5 | 0 | 0.5 | 1.5 | 1 |  | Pic and copy due from Charles
3.9 |  | Info: Policies | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3 |  | David to revise with check by Charles
3.1 |  | Info: Terms | 0.5 |  |  | 0.5 | 2 |  |  | 2 |  |  |  | 0 | 2.5 | 0 | 0 | 2.5 | 2.5 |  | Charles to revise. Legal opinion necessary?
3.11 | * | Sitemap | 1 |  | 1 | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 1 | 1 | 0
3.12 |  | Contact Us | 1 |  | 0.5 | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 0 | 1.5 | 0 | 0.5 | 1.5 | 1
3.13 |  | Change from cookies to local storage use | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
3.14 |  | Add browser version warnings | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
3.15 |  | Add Testimonials page |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.16 |  | Misc | 3 |  |  | 3 |  |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3
|  |  | 27.7 | 0 | 11 | 16.7 | 22.2 | 0 | 3 | 19.2 | 3 | 0 | 0 | 3 | 52.9 | 0 | 14 | 52.9 | 38.9
Ref | F | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
BDT - Braiins DeskTop
4 | * | Initial framework up incl Close | 4 |  | 4 | 0 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 4 | 4 | 0 | 2011-02-27
4.1 |  | Actions: Logout | 0.2 |  |  | 0.2 |  |  |  | 0 |  |  |  | 0 | 0.2 | 0 | 0 | 0.2 | 0.2
4.2 |  | Actions: Fullscreen | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0.5 | 2008-06-17 | A trivial task!
4.3 | * | Actions: Minimise all open windows | 0.1 |  | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.1 | 0 | 0.1 | 0.1 | 0
4.4 |  | Actions: Change Entity | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
4.5 |  | Accounts: Set Current Year | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0.5 |  | When credits are charged
4.6 |  | Accounts: Upload Data | 2 |  |  | 2 | 28 |  | 11 | 17 |  |  |  | 0 | 30 | 0 | 11 | 30 | 19 |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
4.7 |  | Accounts: Edit Data | 21 |  |  | 21 | 10 |  |  | 10 |  |  |  | 0 | 31 | 0 | 0 | 31 | 31 |  | Includes taxonomy stuff and prompted user tagging of text where appropriate/necessary
4.8 |  | Accounts: Generate Accounts | 28 |  |  | 28 | 60 |  | 14 | 46 |  |  |  | 0 | 88 | 0 | 14 | 88 | 74 |  | Report generator by D plus formats by C incl taxonomy info
4.1 |  | Accounts: Download Accounts | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
4.11 |  | Accounts: Export Data | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
4.12 |  | Accounts: Tagging Reports | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6 | 6
4.13 |  | Entities: Change Entity | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
4.14 |  | Entities: New Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
4.15 |  | Entities: Edit, Reset, Delete Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
4.16 |  | Entities: Entities List | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
4.17 |  | Interaction: Messages | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6 | 6
4.18 |  | Interaction: Support | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3 |  | Based on task 4.17
4.19 |  | Interaction: Documentation | 2 |  |  | 2 | 7 |  |  | 7 |  |  |  | 0 | 9 | 0 | 0 | 9 | 9 |  | Charles to write. Initial version only
4.2 |  | Interaction: Training | 2 |  |  | 2 | 7 |  |  | 7 |  |  |  | 0 | 9 | 0 | 0 | 9 | 9 |  | Charles to write. Initial version only
4.21 |  | Preferences: Headings | 6 |  | 5 | 1 | 1 |  |  | 1 |  |  |  | 0 | 7 | 0 | 5 | 7 | 2 |  | Most of the time was choosing and learning tools time.
4.22 |  | Preferences; Layout Options | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6 | 6
4.23 |  | Admin: Agent Details (Account) | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3
4.24 |  | Admin: Administrator | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
4.25 |  | Admin: Staff | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3
4.26 |  | Admin: Credits | 5 |  |  | 5 | 3 |  |  | 3 |  |  |  | 0 | 8 | 0 | 0 | 8 | 8 |  | Includes payment processing interaction
4.27 |  | Admin: Download Export Format | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1 |  | Charles' work for this is in task 4.6
4.28 |  | Admin: Admin Reports | 3 |  |  | 3 | 1 |  |  | 1 |  |  |  | 0 | 4 | 0 | 0 | 4 | 4
4.29 |  | jDesktop tidying up | 5 |  |  | 5 |  |  |  | 0 |  |  |  | 0 | 5 | 0 | 0 | 5 | 5
4.3 |  | Misc | 5 |  |  | 5 | 3 |  |  | 3 |  |  |  | 0 | 8 | 0 | 0 | 8 | 8
|  |  | 116.8 | 0 | 9.1 | 107.7 | 127 | 0 | 25 | 102 | 0 | 0 | 0 | 0 | 243.8 | 0 | 34.1 | 243.8 | 209.7
Ref | F | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
Blog
5 |  | Set it up with logo etc @ blog.braiins.com | 4 |  |  | 4 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 4 | 4
5.1 |  | Enable Braiins Newsletter sign up | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2 |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
5.2 |  | Write and post launch blogs | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3
5.3 |  | Write and post blogs post launch |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Ongoing after launch
|  |  | 7 | 0 | 0 | 7 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 9
Admin
6 |  | Set up an Admin Desktop @ admin.braiins.com | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2 |  | Based on BDT
6.1 |  | Edit people esp password | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1 |  | Based on task 4.25
6.2 |  | Support Message System | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
6.3 |  | Credits Journals | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
6.4 |  | Report: Agents & Entities | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
6.5 |  | Report: Credits i.e. Money Stuff | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
6.6 |  | Report: Site Usage and Tracking Stuff | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
6.7 |  | Housekeeping (End of Day) cron task | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
6.8 |  | Down for maintenance page |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 9.5 | 0 | 0 | 9.5 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10.5 | 0 | 0 | 10.5 | 10.5
Marketing
7 |  | Setup Google Analytics & add code to main pages | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
7.1 |  | Submit to SEs | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
7.2 |  | Issue Press Releases | 0.5 |  |  | 0.5 | 1 |  |  | 1 |  |  |  | 0 | 1.5 | 0 | 0 | 1.5 | 1.5
7.3 |  | Contact AccMan, AW, AA etc | 0.5 |  |  | 0.5 | 1 |  |  | 1 |  |  |  | 0 | 1.5 | 0 | 0 | 1.5 | 1.5
7.4 |  | More, much more…. | 2 |  |  | 2 | 10 |  |  | 10 | 10 |  |  | 10 | 22 | 0 | 0 | 22 | 22
|  |  | 4 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | 10 | 0 | 0 | 10 | 26 | 0 | 0 | 26 | 26
Launch Preparation
8 |  | Test and fix, test and fix incl cross browser issues | 14 |  |  | 14 | 7 |  |  | 7 |  |  |  | 0 | 21 | 0 | 0 | 21 | 21
8.1 |  | Get HMRC approval | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4 | 4
8.2 |  | Set up deployment server | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1 |  | Incl gzip
8.3 |  | Tidy & minimise JS, CSS, HTML + optimise | 3 |  |  | 3 |  |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3
8.4 |  | Get SSL certificate and get SSL working | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 | 3
8.5 |  | Remove authorisation login |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 minutes!
8.6 |  | Finalise payment processing | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4 | 4
8.7 |  | Misc | 5 |  |  | 5 | 5 |  |  | 5 |  |  |  | 0 | 10 | 0 | 0 | 10 | 10
|  |  | 29 | 0 | 0 | 29 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 46 | 46
| 8 | Totals and Ready to LAUNCH Day | 210 | 0 | 32.1 | 177.9 | 198.2 | 0 | 32 | 166.2 | 13 | 0 | 0 | 13 | 421.2 | 0 | 64.1 | 421.2 | 357.1 | 2011-10-01 13:12 | Based on djh "To Do" days
|  | Total days incl Var, % done | 210 | 15.29% |  | 0 | 198.2 | 16.15% |  | 0 | 13 | 0% |  | 0 | 421.2 | 15.22% |  |  | 0
|  | Available days (effective days) |  |  | 31.7143 |  |  |  | 31.7143
|  | Check - should be approx 0 |  |  | -0.38571 |  |  |  | -0.28571
Ref | F | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | E + V | To Do
Post Launch
9 |  | Add Testimonials page
9.1 |  | Write and post blogs post launch
9.2 |  | Down for maintenance page
Niceties Not Essential for Launch
10 |  | Add effects to main site menu | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 | 2
10.1 |  | Add a password strength bar to registration | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1 |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
|  |  | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 | 1
[6 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Ongoing after launch
Notes:
Projected Ready for Launch Date at time of issue
Document Issue History | [19 empty] | 2011-10-01
09 Mar 11 First issue
Formulas:
Est/Act Date = U2+[To Do]*T6-1