## Dev
Braiins Development Schedule |  |  |  |  | All times in days | [12 empty] | Revised: | 2012-01-01 | Date of last addition of tasks or change in the estimated times.
[18 empty] | Last update: | 2012-01-01 | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [12 empty] | Start Date: | 2011-02-01 | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [12 empty] | Launch Date: | 2013-01-16 16:00 | Projected Ready to Launch Date
Postponed to post launch |  |  |  | Done: | Days completed
Could be postponed to post launch if necessary |  |  |  | To Do: | Days remaining to be done | [12 empty] | 1.1667 | 6 | Average effective development days per week
E = Exclude from 'To Do' calcs
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Admin Stuff
1 |  | Choose Name and buy domains | 1 |  | 1 | 0 | 2 |  | 2 | 0 |  |  |  |  | 3 | 0 | 3 | 0 | 2011-02-06 | Braiins chosen
1.1 |  | Set up Braiins Ltd UK |  |  |  | 0 | 2 |  | 2 | 0 |  |  |  |  | 2 | 0 | 2 | 0
1.2 |  | Sort out ElanElan or other IBC | 2 |  | 1 | 1 |  |  |  | 0 |  |  |  |  | 2 | 0 | 1 | 1
1.3 |  | Accounting, VAT, legal, banking etc admin stuff |  |  |  | 0 | 5 |  |  | 5 |  |  |  |  | 5 | 0 | 0 | 5
1.4 |  | HMRC Registered |  |  |  | 0 | 2 |  |  | 2 |  |  |  |  | 2 | 0 | 0 | 2
1.5 |  | Other? | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  |  | 3 | 0 | 0 | 3
|  |  | 4 | 0 | 2 | 2 | 13 | 0 | 4 | 9 | 0 | 0 | 0 | 0 | 17 | 0 | 6 | 11
Project
2 |  | Initial Plans | 2 |  | 2 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 3 | 0 | 3 | 0 | 2011-02-03 | Main site plus Braiins Desktop
2.1 |  | Tools Selection | 8 |  | 6 | 2 |  |  |  | 0 |  |  |  | 0 | 8 | 0 | 6 | 2 |  | html 5, JavaScript, PHP, MySQL, jQuery, jDesktop, SlickGrid, WordPress, UniServer + various other jQuery plugins
2.2 |  | Initial Database design | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 0 | 2011-02-14
2.3 |  | Choose Payment Processing Service(s) | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4
2.3 |  | Choose Hosting | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2
2.4 |  | Research, Thinking, Communicating, Negotiating | 50 |  | 23 | 27 | 120 |  | 60 | 60 |  |  |  | 0 | 170 | 0 | 83 | 87
|  |  | 64 | 0 | 33 | 31 | 125 | 0 | 61 | 64 | 0 | 0 | 0 | 0 | 189 | 0 | 94 | 95
Main Braiins.com Site
3 |  | Initial framework up | 7 |  | 7 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 8 | 0 | 8 | 0 | 2011-02-14
3.1 |  | Logo, favicon, colours, layout/design | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 9 | 0 | 0 | 9 |  | Via Freelancer.com? Use template?
3.2 |  | Home Page | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 9 | 0 | 0 | 9 |  | Strap line, copy, images + slide show or video?
3.3 |  | Free Trial | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Small task as currently envisaged
3.4 |  | Registration | 5 |  | 3 | 2 | 3 |  | 2 | 1 |  |  |  | 0 | 8 | 0 | 5 | 3 |  | Terms of Service to be updated once task 3.10 is final. Guarantee to be agreed. Add pw strength check?
3.5 |  | Info: Features & Benefits | 1 |  |  | 1 | 5 |  |  | 5 |  |  |  | 0 | 6 | 0 | 0 | 6 |  | Charles to write. Incl BDT images as per current Tari page?
3.6 |  | Info: Prices | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4 |  | Charles to research and write
3.7 |  | Info: FAQs | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Charles to write
3.8 |  | Info: About Us | 2 |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 1 | 2 |  | Pic and copy due from Charles
3.9 |  | Info: Policies | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | David to revise with check by Charles
3.1 |  | Info: Terms | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Charles to revise. Legal opinion necessary?
3.11 |  | Sitemap | 1 |  | 1 | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 1 | 0
3.12 |  | Contact Us | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2
3.13 | E | Change from cookies to local storage use | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
3.14 |  | Add browser version warnings | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
3.15 | E | Add Testimonials page | 3 |  |  | 0 | 3 |  |  | 0 |  |  |  | 0 | 6 | 0 | 0 | 0
3.16 |  | Misc | 3 |  |  | 3 | 3 |  |  | 3 |  |  |  | 0 | 6 | 0 | 0 | 6
|  |  | 37 | 0 | 12 | 20 | 33 | 0 | 3 | 27 | 6 | 0 | 0 | 6 | 76 | 0 | 15 | 53
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
UK-GAAP Taxonomy and BROs
4 |  | Taxonomy DB and associated Admin Utils | 60 |  | 60 | 0 | 28 |  | 28 | 0 |  |  |  | 0 | 88 | 0 | 88 | 0
4.1 |  | Bros system | 72 |  | 60 | 12 | 28 |  | 28 | 0 |  |  |  | 0 | 100 | 0 | 88 | 12 |  | Including SS Export/Import and summing. StartEnd summing to be finalised once Bros have been created.
4.1 |  | Create Bros | 21 |  | 21 | 0 | 90 |  | 28 | 62 |  |  |  | 0 | 111 | 0 | 49 | 62 |  | Including Bros Tree
4.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 160 | 0 | 141 | 19 | 153 | 0 | 84 | 69 | 0 | 0 | 0 | 0 | 313 | 0 | 225 | 88
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Import - SAPA Initially
5 |  | SAPA export format | 2 |  | 1 | 1 | 14 |  | 10 | 4 |  |  |  | 0 | 16 | 0 | 11 | 5 |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
5.1 |  | Importing into Braiins | 28 |  | 21 | 7 | 14 |  | 2 | 12 |  |  |  | 0 | 42 | 0 | 23 | 19 |  | Including mapping
5.2 |  | Checking and correcting import data | 28 |  |  | 28 | 7 |  |  | 7 |  |  |  | 0 | 35 | 0 | 0 | 35 |  | General checking system to be used by BDT input/edit too
5.3 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 65 | 0 | 22 | 43 | 42 | 0 | 12 | 30 | 0 | 0 | 0 | 0 | 107 | 0 | 34 | 73
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Accounts Production
6 |  | Report Generator | 84 |  | 60 | 24 |  |  |  | 0 |  |  |  | 0 | 84 | 0 | 60 | 24
6.1 |  | Initial formats | 7 |  | 4 | 3 | 120 |  |  | 120 |  |  |  | 0 | 127 | 0 | 4 | 123
6.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 14 |  |  | 14 |  |  |  | 0 | 21 | 0 | 0 | 21
|  |  | 98 | 0 | 64 | 34 | 134 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 232 | 0 | 64 | 168
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
BDT - Braiins DeskTop
7 |  | Initial framework up incl Close | 7 |  | 7 | 0 |  |  |  | 0 |  |  |  | 0 | 7 | 0 | 7 | 0 | 2011-02-27
7.01 |  | Actions: Logout | 0.2 |  | 0.2 | 0 |  |  |  | 0 |  |  |  | 0 | 0.2 | 0 | 0.2 | 0 | 2012-01-01
7.02 |  | Actions: Fullscreen | 0.5 | -0.4 | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.5 | -0.4 | 0.1 | 0 | 2012-01-01 | Done simply via a hint to press F11
7.03 |  | Actions: Minimise all open windows | 0.1 |  | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.1 | 0 | 0.1 | 0
7.1 |  | Current Entity: Enter or Edit Data | 56 |  |  | 56 | 14 |  | 1 | 13 |  |  |  | 0 | 70 | 0 | 1 | 69 |  | Time to do this will depend a lot on how many and how complex the input screens are.
7.11 |  | Current Entity: Trial Balance | 14 |  |  | 14 | 2 |  | 1 | 1 |  |  |  | 0 | 16 | 0 | 1 | 15 |  | Includes learning time on chosen report producing grid including printing and pdf etc output.
7.12 |  | Current Entity: Data Trail | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  | Similar to current Utils Data Dump in the BDT environment
7.13 |  | Current Entity: Generate Accounts | 7 |  |  | 7 | 2 |  |  | 2 |  |  |  | 0 | 9 | 0 | 0 | 9 |  | Desktop integration of Accounts Production task above
7.14 |  | Current Entity: Download Accounts | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Exactly how still to be decided.
7.15 |  | Current Entity: Upload Data | 4 |  |  | 4 | 2 |  |  | 2 |  |  |  | 0 | 6 | 0 | 0 | 6 |  | Desktop integration of Import task above
7.16 |  | Current Entity: Set Current Year | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | When credits are used up i.e. charged
7.2 |  | Entities: Change Entity | 4 |  |  | 4 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 4 |  | Envisage a searchable table.
7.21 |  | Entities: New Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Form but have to check for unique ref, name and CH #
7.22 |  | Entities: Edit, Reset, Delete Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Administrator permissions required for Reset and Delete.
7.23 |  | Entities: Entities List | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Similar to the Change Entity table but with report options.
7.3 | E | Interaction: Messages | 14 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 15 | 0 | 0 | 0
7.31 | E | Interaction: Support | 2 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0 |  | Based on task 7.30
7.32 | E | Interaction: Documentation | 4 |  |  | 0 | 14 |  |  | 0 |  |  |  | 0 | 18 | 0 | 0 | 0 |  | Initial version only
7.4 |  | Preferences: Headings | 8 |  | 6 | 2 | 1 |  |  | 1 |  |  |  | 0 | 9 | 0 | 6 | 3 |  | Most of the time was choosing and learning tools time.
7.41 |  | Preferences: Layout Options | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6
7.5 |  | Admin: Agent Details (Account) | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
7.51 |  | Admin: Administrator | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Change administrator
7.52 |  | Admin: Staff | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Add/Edit in two tabs
7.53 |  | Admin: Credits | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10 |  | Includes payment processing interaction
7.54 |  | Admin: Download Export Format | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  | Charles' work for this is in task 7.2
7.55 |  | Admin: Admin Reports | 7 |  |  | 7 | 1 |  |  | 1 |  |  |  | 0 | 8 | 0 | 0 | 8 |  | Audit Trail + ?
7.6 |  | jDesktop tidying up | 10 |  |  | 10 |  |  |  | 0 |  |  |  | 0 | 10 | 0 | 0 | 10
7.61 |  | Misc | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10
|  |  | 177.8 | -0.4 | 13.4 | 144 | 50 | 0 | 2 | 32 | 0 | 0 | 0 | 0 | 227.8 | -0.4 | 15.4 | 176
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Blog
8 | E | Set it up with logo etc @ blog.braiins.com | 4 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 0
8.1 | E | Enable Braiins Newsletter sign up | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
8.2 | E | Write and post launch blogs | 1 |  |  | 0 | 2 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0
8.3 | E | Write and post blogs post launch |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | Ongoing after launch
|  |  | 7 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
Admin
9 | E | Set up an Admin Desktop @ admin.braiins.com | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 |  | Based on BDT
9.1 | E | Edit people esp password | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 |  | Based on task 7.52
9.2 | E | Support Message System | 1 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
9.3 | E | Credits Journals | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.4 | E | Report: Agents & Entities | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.5 | E | Report: Credits i.e. Money Stuff | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.6 | E | Report: Site Usage and Tracking Stuff | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.7 | E | Housekeeping (End of Day) cron task | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
9.8 | E | Down for maintenance page | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
|  |  | 11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
Marketing
10 |  | Setup Google Analytics & add code to main pages | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
10.1 |  | Submit to SEs | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
10.2 |  | Issue Press Releases | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3
10.3 |  | Contact AccMan, AW, AA etc | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
10.4 | E | More, much more…. | 2 |  |  | 0 | 10 |  |  | 0 |  |  |  | 0 | 12 | 0 | 0 | 0
|  |  | 6 | 0 | 0 | 4 | 12 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 6
Launch Preparation
11 |  | Test and fix, test and fix incl cross browser issues | 14 |  |  | 14 | 7 |  |  | 7 |  |  |  | 0 | 21 | 0 | 0 | 21
11.1 |  | Get HMRC approval | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4
11.2 |  | Set up deployment server | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  | Incl gzip
11.3 |  | Tidy & minimise JS, CSS, HTML + optimise | 3 |  |  | 3 |  |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 3
11.4 |  | Get SSL certificate and get SSL working | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
11.5 |  | Remove authorisation login |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2 minutes!
11.6 |  | Finalise payment processing | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4
11.7 |  | Misc | 7 |  |  | 7 | 5 |  |  | 5 |  |  |  | 0 | 12 | 0 | 0 | 12
|  |  | 31 | 0 | 0 | 31 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 48
12 |  | Unallocated Braiins Days | 0 |  | 0 | 0 | 209.55 |  | 121.1429 | 88.4072 |  |  |  | 0 | 209.55 | 0 | 121.1429 | 88.4072 |  | 'Done' days calculated as difference between Available and Total days below.
|  | Totals and Ready to LAUNCH Day | 660.8 | -0.4 | 287.4 | 328 | 582 | 0 | 166 | 472.4072 | 6 | 0 | 0 | 6 | 1458.35 | -0.4 | 574.5429 | 806.4072 | 2013-01-16 16:00 | Based on D "To Do" days
|  | Total days incl Var, % done | 660.4 | 43.52% |  |  | 582 | 28.52% |  |  | 6 | 0% |  | 0 | 1457.95 | 39.41% |  |  | 2013-07-04 03:24 | Based on C "To Do" days
|  | Available days (effective days) |  |  | 287.1429 |  |  |  | 287.1429 |  |  |  |  | -6
| E | Excluded Task Days |  |  | 45 |  |  |  | 32 |  |  |  |  | 0 |  |  | 77
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Post Launch
13 |  | Add Testimonials page | [15 empty] | 0
13.1 |  | Write and post blogs post launch | [15 empty] | 0
13.2 |  | Down for maintenance page | [15 empty] | 0
13.3 |  | Admin site
13.4 |  | Video on HP | [15 empty] | 0
13.5 |  | Ongoing…..
Notes:
Document Issue History | [18 empty] | Projected Ready for Launch Date at time of issue
09 Mar 11 First issue | [18 empty] | 2011-10-01 | Dreaming!
02 Jan 12 | [18 empty] | 2013-07-04 | Need to improve on this
Formulas:
Est/Act Date = T2+[To Do]*S6-1
Est/Act Date = T2+[To Do, row above]*S6-1