## Dev
Braiins Development Schedule |  |  |  |  | All times in days | [12 empty] | Revised: | 2012-04-14 | Date of last addition of tasks or change in the estimated times.
[18 empty] | Last update: | 2012-04-14 | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [12 empty] | Start Date: | 2011-02-01 | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [12 empty] | Launch Date: | 2013-01-21 12:00 | Projected Ready to Launch Date for Version 0.1
|  |  |  | Done: | Days completed | [12 empty] | Version: | 0.1
| V = Version |  |  | To Do: | Days remaining to be done | [12 empty] | 1.1667 | 6 | Average effective development days per week
Ref | V | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Admin Stuff
1 | 0.1 | Choose Name and buy domains | 1 |  | 1 | 0 | 2 |  | 2 | 0 |  |  |  |  | 3 | 0 | 3 | 0 | 2011-02-06 | Braiins chosen
1.1 | 0.1 | Set up Braiins Ltd UK |  |  |  | 0 | 2 |  | 2 | 0 |  |  |  |  | 2 | 0 | 2 | 0
1.2 | 0.1 | Sort out company structure | 2 |  | 1 | 1 |  |  |  | 0 |  |  |  |  | 2 | 0 | 1 | 1 |  | IPR company and operating company?
1.3 | 0.1 | Accounting, VAT, legal, banking etc admin stuff |  |  |  | 0 | 5 |  |  | 5 |  |  |  |  | 5 | 0 | 0 | 5
1.4 | 0.1 | HMRC Registered |  |  |  | 0 | 2 |  |  | 2 |  |  |  |  | 2 | 0 | 0 | 2
1.5 | 0.1 | Other? | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  |  | 3 | 0 | 0 | 3
1.6 | 0.1 | D move to Australia incl UK time | 28 |  | 28 | 0 | 7 |  | 7 | 0 |  |  |  |  | 35 | 0 | 35 | 0
|  |  | 32 | 0 | 30 | 2 | 20 | 0 | 11 | 9 | 0 | 0 | 0 | 0 | 17 | 0 | 6 | 11
Project
2 | 0.1 | Initial Plans | 2 |  | 2 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 3 | 0 | 3 | 0 | 2011-02-03 | Main site plus Braiins Desktop
2.1 | 0.1 | Tools Selection | 8 |  | 6 | 2 |  |  |  | 0 |  |  |  | 0 | 8 | 0 | 6 | 2 |  | html 5, JavaScript, PHP, MySQL, jQuery, jDesktop, DataTable, WordPress, WampServer + various other jQuery plugins. Ext Js?
2.2 | 0.1 | Initial Database design | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 0 | 2011-02-14
2.3 | 0.1 | Choose Payment Processing Service(s) | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4
2.3 | 0.1 | Choose Hosting | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2
2.4 | 0.1 | Research, Thinking, Communicating, Negotiating | 30 |  | 22 | 8 | 220 |  | 198 | 22 |  |  |  | 0 | 250 | 0 | 220 | 30 |  | Including SBR long term thinking, feedback to HMRC, potential JVs/collaboration, unallocated time, etc.
|  |  | 44 | 0 | 32 | 12 | 225 | 0 | 199 | 26 | 0 | 0 | 0 | 0 | 269 | 0 | 231 | 38
Main Braiins.com Site
3 | 0.1 | Initial framework up | 7 |  | 7 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 8 | 0 | 8 | 0 | 2011-02-14
3.1 | 0.1 | Logo, favicon, colours, layout/design | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 9 | 0 | 0 | 9 |  | Via Freelancer.com? Use template?
3.2 | 0.1 | Home Page | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 9 | 0 | 0 | 9 |  | Strap line, copy, images + slide show or video?
3.3 | 0.1 | Free Trial | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Small task as currently envisaged
3.4 | 0.1 | Registration | 5 |  | 3 | 2 | 3 |  | 2 | 1 |  |  |  | 0 | 8 | 0 | 5 | 3 |  | Terms of Service to be updated once task 3.10 is final. Guarantee to be agreed. Add pw strength check?
3.5 | 0.1 | Info: Features & Benefits | 1 |  |  | 1 | 5 |  |  | 5 |  |  |  | 0 | 6 | 0 | 0 | 6 |  | Charles to write. Incl BDT images as per current Tari page?
3.6 | 0.1 | Info: Prices | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4 |  | Charles to research and write
3.7 | 0.1 | Info: FAQs | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Charles to write
3.8 | 0.1 | Info: About Us | 2 |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 1 | 2 |  | Pic and copy due from Charles
3.9 | 0.1 | Info: Policies | 2 |  | 1 | 1 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 1 | 3 |  | David to revise with check by Charles
3.1 | 0.1 | Info: Terms | 2 |  | 1 | 1 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 1 | 3 |  | Charles to revise. Legal opinion necessary?
3.11 | 0.1 | Sitemap | 1 |  | 1 | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 1 | 0
3.12 | 0.1 | Contact Us | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2
3.13 | 0.1 | Change from cookies to local storage use | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 0
3.14 | 0.1 | Add browser version warnings | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  | Allow only FF, Chrome, Safari?
3.15 | 0.1 | Add Testimonials page | 3 |  |  | 3 | 3 |  |  | 3 |  |  |  | 0 | 6 | 0 | 0 | 6
3.16 | 0.1 | Convert all current xhtml pages to html5 | 2 | -1 | 1 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | -1 | 1 | 0 | 2012-01-07
3.17 | 0.1 | Misc as per D's ToDo.txt doc | 3 |  |  | 3 |  |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 3
|  |  | 41 | -1 | 17 | 23 | 30 | 0 | 3 | 27 | 6 | 0 | 0 | 6 | 77 | -1 | 20 | 56
Ref | V | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
UK-GAAP Taxonomy and BROs
4 | 0.1 | Taxonomy DB and associated Admin Utils | 60 |  | 60 | 0 | 28 |  | 28 | 0 |  |  |  | 0 | 88 | 0 | 88 | 0
4.1 | 0.1 | Bros system | 72 |  | 65 | 7 | 28 |  | 28 | 0 |  |  |  | 0 | 100 | 0 | 93 | 7 |  | Including SS Export/Import and summing. StartEnd summing to be finalised once Bros have been created.
4.2 | 0.1 | Create Bros | 21 |  | 21 | 0 | 90 | 18 | 90 | 18 |  |  |  | 0 | 111 | 18 | 111 | 18 |  | Including Bros Tree
4.3 | 0.1 | Restructure Bros with pseudo CoA | 2 |  |  | 2 | 10 | 4 | 2 | 12 |  |  |  | 0 | 12 | 4 | 2 | 14 |  | De-constructed as at 12.04.12 -> re-constructing. As part of this will put in a CoA feature
4.4 | 0.1 | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 162 | 0 | 146 | 16 | 163 | 22 | 148 | 37 | 0 | 0 | 0 | 0 | 325 | 22 | 294 | 53
Ref | V | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Import - SAPA Initially
5 | 0.1 | SAPA export format | 2 |  | 1 | 1 | 14 |  | 10 | 4 |  |  |  | 0 | 16 | 0 | 11 | 5 |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
5.1 | 0.1 | Importing into Braiins | 28 |  | 21 | 7 | 14 |  | 3 | 11 |  |  |  | 0 | 42 | 0 | 24 | 18 |  | Including mapping
5.2 | 0.1 | Checking and correcting import data | 28 |  |  | 28 | 7 |  |  | 7 |  |  |  | 0 | 35 | 0 | 0 | 35 |  | General checking system to be used by BDT input/edit too
5.3 | 0.1 | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 65 | 0 | 22 | 43 | 42 | 0 | 13 | 29 | 0 | 0 | 0 | 0 | 107 | 0 | 35 | 72
Ref | V | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Accounts Production
6 | 0.1 | Report Generator | 84 |  | 60 | 24 | 7 |  |  | 7 |  |  |  | 0 | 91 | 0 | 60 | 31
6.1 | 0.1 | Initial formats | 14 |  | 4 | 10 | 70 |  |  | 70 |  |  |  | 0 | 84 | 0 | 4 | 80 |  | Covers bulk of formats but in a fixed style. Recreating UK GAAP taxonomy straight-forward. Though may leave out truly obscure reports. If ability to do things such as Restated and Discontinued Acquired is time consuming then would look to leave them out
6.2 | 0.2 | Later formats | 7 |  |  | 0 | 30 |  |  | 0 |  |  |  | 0 | 37 | 0 | 0 | 0 |  | Put in anything left out from above e.g. Restated, Discontinued/Acquired, Consolidations.
6.3 | 0.2 | Rounding | 7 |  |  | 0 | 30 |  |  | 0 |  |  |  | 0 | 37 | 0 | 0 | 0 |  | Rounding within Braiins as opposed to importing rounded numbers. Probably will involve Bro summing as well as RG.
6.4 | 0.3 | Style options | 28 |  |  | 0 | 7 |  |  | 0 |  |  |  | 0 | 35 | 0 | 0 | 0 |  | Provide update which gives user control over layout e.g. number of columns, fonts, point size and colours
6.5 | 3 | Graphics | 28 |  |  | 0 | 7 |  |  | 0 |  |  |  | 0 | 35 | 0 | 0 | 0 |  | Put in the pretty pictures
|  |  | 168 | 0 | 64 | 34 | 151 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 319 | 0 | 64 | 111
Ref | V | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
BDT - Braiins DeskTop
7 | 0.1 | Initial framework up incl Close | 7 |  | 7 | 0 | [7 empty] | 0 | 7 | 0 | 7 | 0 | 2011-02-27
7.01 | 0.1 | Actions: Logout | 0.2 |  | 0.2 | 0 | [7 empty] | 0 | 0.2 | 0 | 0.2 | 0 | 2012-01-01
7.02 | 0.1 | Actions: Fullscreen | 0.5 | -0.4 | 0.1 | 0 | [7 empty] | 0 | 0.5 | -0.4 | 0.1 | 0 | 2012-01-01 | Done simply via a hint to press F11
7.03 | 0.1 | Actions: Minimise all open windows | 0.1 |  | 0.1 | 0 | [7 empty] | 0 | 0.1 | 0 | 0.1 | 0
7.04 | 0.1 | Actions: Close all open windows | 0.1 |  | 0.1 | 0 | [7 empty] | 0 | 0.1 | 0 | 0.1 | 0
7.05 | 0.1 | Current Entity: Upload Data | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5
7.06 | 0.1 | Current Entity: Enter or Edit Data - Simple | 28 |  |  | 28 | 7 |  |  | 7 |  |  |  | 0 | 35 | 0 | 0 | 35 |  | Simple edit incl schedule via 6a method for version 0.1
7.07 | 0.2 | Current Entity: Enter or Edit Data - Full | 56 |  |  | 0 | 14 |  |  | 0 |  |  |  | 0 | 70 | 0 | 0 | 0 |  | Time to do this will depend a lot on how many and how complex the input screens are.
7.08 | 0.1 | Current Entity: Trial Balance | 7 |  |  | 7 | 2 |  | 1 | 1 |  |  |  | 0 | 9 | 0 | 1 | 8 |  | Similar to current Utils Trial Balance but extended
7.09 | 0.1 | Current Entity: Data Trail | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  | Similar to current Utils Data Dump
7.1 | 0.1 | Current Entity: Data Check | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  | Same as check run after an Import?
7.11 | 0.1 | Current Entity: Financial Statements | 7 |  | 6 | 1 |  |  |  | 0 |  |  |  | 0 | 7 | 0 | 6 | 1
7.12 | 0.1 | Current Entity: FS Download | 6 |  | 6 | 0 |  |  |  | 0 |  |  |  | 0 | 6 | 0 | 6 | 0 | 2012-02-13
7.13 | 0.1 | Current Entity: Set to Final | 3 |  | 3 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 4 | 0 | 4 | 0 | 2012-02-14
7.14 | 0.2 | Current Entity: Start New Year | 6 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 7 | 0 | 0 | 0 |  | When credits are used up i.e. charged
7.15 | 0.1 | Entities: Change | 4 |  | 4 | 0 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 4 | 0 | 2012-01-05
7.16 | 0.1 | Entities: List | 7 | 14 | 21 | 0 |  |  |  | 0 |  |  |  | 0 | 7 | 14 | 21 | 0 | 2012-01-19 | Includes separate tab work
7.17 | 0.1 | Entities: New | 4 |  |  | 4 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 4 |  | Form but have to check for unique ref, name and CH #. Includes a credit charge.
7.18 | 0.1 | Entities: Edit | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Form but have to check for unique ref, name and CH #
7.19 | 0.1 | Entities: Reset | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 0
7.2 | 0.1 | Entities: Delete | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 0 |  | Administrator permissions required
7.21 | 1 | Interaction: Messages | 14 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 15 | 0 | 0 | 0 |  | Administrator permissions required
7.22 | 1 | Interaction: Support | 14 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 15 | 0 | 0 | 0
7.23 | 1 | Interaction: Documentation | 2 |  |  | 0 | 28 |  |  | 0 |  |  |  | 0 | 30 | 0 | 0 | 0 |  | Based on task 7.22
7.24 | 0.1 | Admin: Agent Details (Account) | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  | Initial version only
7.25 | 0.1 | Admin: Headings | 8 |  | 6 | 2 | 1 |  |  | 1 |  |  |  | 0 | 9 | 0 | 6 | 3
7.26 | 1 | Admin: Layout Options | 5 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 6 | 0 | 0 | 0
7.27 | 0.1 | Admin: Administrator | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Change administrator
7.28 | 0.1 | Admin: Staff | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | Add/Edit in two tabs
7.29 | 0.1 | Admin: Credits | 7 |  |  | 7 | 1 |  |  | 1 |  |  |  | 0 | 8 | 0 | 0 | 8 |  | Includes payment processing interaction
7.3 | 0.1 | Admin: Download Export Format | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  | Charles' work for this is in task 5.0 SAPA export format
7.31 | 0.1 | Admin: Admin Reports | 7 |  |  | 7 |  |  |  | 0 |  |  |  | 0 | 7 | 0 | 0 | 7 |  | Audit Trail + ?
7.32 | 0.1 | jDesktop tidying up | 10 |  | 7 | 3 | 1 |  |  | 1 |  |  |  | 0 | 11 | 0 | 7 | 4
7.33 | 0.1 | Misc as per D's ToDo.txt doc | 7 |  | 1 | 6 | 1 |  |  | 1 |  |  |  | 0 | 8 | 0 | 1 | 7
7.34 | 0.2 | Change to Ext Js? | 21 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 21 | 0 | 0 | 0 |  | Needed for 7.07 Current Entity: Enter or Edit Data - Full ?
|  |  | 257.9 | 13.6 | 65.5 | 88 | 66 | 0 | 2 | 18 | 0 | 0 | 0 | 0 | 323.9 | 13.6 | 67.5 | 106
Ref | V | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Blog
8 | 1 | Set it up with logo etc @ blog.braiins.com | 4 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 0
8.1 | 1 | Enable Braiins Newsletter sign up | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
8.2 | 1 | Write and post launch blogs | 1 |  |  | 0 | 2 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0
8.3 | 1 | Write and post blogs post launch |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | Ongoing after launch
|  |  | 7 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
Admin
9 | 1 | Set up an Admin Desktop @ admin.braiins.com | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 |  | Based on BDT
9.1 | 1 | Edit people esp password | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 |  | Based on task 7.29
9.2 | 1 | Support Message System | 1 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
9.3 | 1 | Credits Journals | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.4 | 1 | Report: Agents & Entities | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.5 | 1 | Report: Credits i.e. Money Stuff | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.6 | 1 | Report: Site Usage and Tracking Stuff | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.7 | 1 | Housekeeping (End of Day) cron task | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
9.8 | 1 | Down for maintenance page | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
|  |  | 11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
Marketing
10 | 1 | Setup Google Analytics & add code to main pages | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
10.1 | 1 | Submit to SEs | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
10.2 | 1 | Issue Press Releases | 1 |  |  | 0 | 2 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0
10.3 | 1 | Contact AccMan, AW, AA etc | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
10.4 | 1 | More, much more…. | 2 |  |  | 0 | 10 |  |  | 0 |  |  |  | 0 | 12 | 0 | 0 | 0
|  |  | 6 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0
Launch Preparation
11 | 0.1 | Test and fix, test and fix incl cross browser issues | 14 | -7 |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 21 | -7 | 0 | 14 |  | Reduced for decision to exclide IE
11.1 | 0.1 | Get HMRC approval | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4
11.2 | 0.1 | Set up deployment server | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | Incl gzip
11.3 | 0.1 | Tidy & minimise JS, CSS, HTML + optimise | 3 |  |  | 3 |  |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 3
11.4 | 0.1 | Get SSL certificate and get SSL working | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
11.5 | 0.1 | Remove authorisation login |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2 minutes!
11.6 | 0.1 | Finalise payment processing | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4
11.7 | 0.1 | Misc | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14 |  | As per D's ToDo.txt doc for D
|  |  | 32 | -7 | 0 | 25 | 19 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 51 | -7 | 0 | 44
12 |  | Unallocated Braiins Days | -0.21416 |  | -0.21429 | 0.00012196 | 0.28593 |  | 0.28571 | 0.00021711 |  |  |  | 0 | 0.071768 | 0 | 0.071429 | 0.00033907 |  | 'Done' days calculated as difference between Available and Total days below. Should be zero or close to zero.
|  | Totals and Ready to LAUNCH Day | 825.9 | 5.6 | 376.5 | 243.0001 | 731 | 22 | 376 | 242.0002 | 6 | 0 | 0 | 6 | 1527.9718 | 27.6 | 717.5714 | 491.0003 | 2013-01-21 12:00 | Based on D "To Do" days
|  | Total days incl Var, % done | 831.5 | 45.28% |  |  | 753 | 49.93% |  |  | 6 | 0% |  | 0 | 1555.5718 | 46.13% |  |  | 2013-01-20 08:00 | Based on C "To Do" days
|  | Available days (effective days) |  |  | 376.2857 |  |  |  | 376.2857 |  |  |  |  | -6
Notes:
Document Issue History | [18 empty] | Projected Ready for Launch Date at time of issue
09 Mar 11 First issue | [18 empty] | 2011-10-01 | Dreaming!
02 Jan 12 | [18 empty] | 2013-07-04 | Need to improve on this
14 Apr 12 | [18 empty] | 2013-01-21 | For Version 0.1
14 Apr 12 | [18 empty] | 2013-05-14 | For Version 0.2
14 Apr 12 | [18 empty] | 2013-08-11 | For Version 1.0
Formulas:
Est/Act Date = T2+[To Do]*S6-1
Est/Act Date = T2+[To Do, row above]*S6-1

## Versions
Started as CW Thoughts 12.04.2012, Revised by djh below |  | Thoughts from 9 April email "A Few Braiins Thoughts"
DESIGN MAXIM | Simply true, truly beautiful | 1. No Edit from the face of the accounts
As with H.A, Braiins is about control, repeatability, and efficiency = no free form editing of generated accounts.
VERSION | SUMMARY
.01 | Simple SAPA XBRL bolt on v1 | Instead of anything goes editing from the face of the accounts (especially XBRL Edit as in OAP!), edit the source data, with control re DE balance
| Covers bulk of formats but in a fixed style. Recreating UK GAAP taxonomy straight-forward. Cover most common and easy. | and dimension etc use, and an audit trail of the edits, and re-generate the accounts quickly on demand in a separate tab, though not for every edit,
so that the effect of changes can be seen whenever wanted.
0.2 | Simple SAPA XBRL bolt on v2
| Put in any formats left out from above e.g. Restated, Discontinued/Acquired, Consolidations | Perhaps some controlled editing capability could be added in the future if Drill Down (pt 2) is implemented, but def not for the first few rounds.
1.0 | Equates to SFS | 2. No Drill Down from the face of the accounts
| Control layout of formats: Include/exclude, fonts, columns | The case against this is not as strong as the anti-editing case since it will often be nice to know the source or sources of a particular number
or piece of text, and providing that info would not violate any control principles.
2.0 | Self contained AP system
| Manually enter and edit data. | But the work involved in maintaining the necessary behind the scenes info to allow drill down anywhere is significant, and will appreciably slow
accounts generation. To be considered for a future round.
3.0 | Getting fancy
| Insert graphics? | 3. Rounding
| Insert Objects? | In my response to your SFS comments I said we needed to talk about rounding, but we haven;t done that yet.
4.0 | New Taxonomy 1 | So this is just to flag that we should talk about it. [14.04.12 Covered in version points below left.]
Charities
4. No Mention of any XBRL terms like tuple, dimension etc.
5.0 | New Taxonomy 2 | I think we can make Braiins work without exposing any non-accounting XBRL jargon.
UK-IFRS
5. Smart Import and Mapping
N.n | Ultimate | Being smart about getting the data from SAPA (initially) into BROs with little manual intervention afterwards is key to getting SAPA users
| Objective is to eliminate as many tasks as possible between Entity source and AP output | exposed to SFS singing the praises of Braiins, even at version 0.1.
e.g. Data re-entry, duplicating SSs. Put as much pwer as possible within the BRAIINs itself
| So it become it what its name says. | Doing this may involve fancy mapping and building in some assumptions re memo code use, but it will be pure info from you and back end php
programming by me = easy and fast to develop compared with the pain and slow development of complex screens, yet impressive for the poor
| Provide ability to directly import from all major GL systems | SAPA user exposed to hours or a day to transfer one client to SFS. We should be able to do our transfer in a tiny fraction of the time = a huge
| XBRL In. | difference. Braiins version 0.1 won't look nearly as pretty as SFS or OAP, but will outperform them by a mile.
Cover all English language taxonomies.
6. Schedule Stuff
As Revised/Extended by djh |  | As you know, no schedule (table) type data handling is yet working for Braiins.
VERSION | SUMMARY | There are 3 ways we can go:
.01 | Simple SAPA XBRL bolt on v1 | a. Forms (as many as are required) with any number of defined fields, including tables within the form with defined columns
| Covers bulk of formats but in a fixed style. Recreating UK GAAP taxonomy straight-forward. Cover most common and easy. | and a variable number of rows.
Includes:
| Export from SAPA using SAPA rounding i.e. whole pounds | b. Spread sheet like free form "tables"
Import to Braiins with Bro summing and 'issues' handling as per Thoughts at right point 5.
| Trial Balance | c. An Excel SS with multiple tabs linked to the entity
Data Trail
| Simple edit of Bro data, whole pounds only | a is by far the easiest, and the easiest to control, if it can do the necessary. I will wait for your views on what is necessary to finalise this.
Schedule input/editing as per 6a at the right.
RG for set of common formats -> iXBRL html accounts
0.2 | Simple SAPA XBRL bolt on v2
Put in any formats left out from above e.g. Restated, Discontinued/Acquired, Consolidations
Includes:
Export from SAPA in exact form i.e. pounds and pence
Proper editing within Braiins
Rounding within Braiins
Start New Year
1.0 | Equates to SFS
Control layout of formats: Include/exclude, fonts, columns
2.0 | Self contained AP system
Manually enter and edit data.
3.0 | Getting fancy
Insert graphics?
Insert Objects?
4.0 | New Taxonomy 1
Charities
5.0 | New Taxonomy 2
UK-IFRS
N.n | Ultimate
Objective is to eliminate as many tasks as possible between Entity source and AP output
e.g. Data re-entry, duplicating SSs. Put as much pwer as possible within the BRAIINs itself
So it become it what its name says.
Provide ability to directly import from all major GL systems
XBRL In.
Cover all English language taxonomies.

## Details
CW Thoughts 12.04.2012
Braiins Development Schedule |  |  |  |  | All times in days | [12 empty] | Revised: | 2012-01-01 |  | Date of last addition of tasks or change in the estimated times.
[18 empty] | Last update: | 2012-01-01 |  | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [12 empty] | Start Date: | 2011-02-01 |  | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [12 empty] | Launch Date: | #REF! |  | Projected Ready to Launch Date
Postponed to post launch |  |  |  | Done: | Days completed
Could be postponed to post launch if necessary |  |  |  | To Do: | Days remaining to be done | [12 empty] | 1.1667 | 6 |  | Average effective development days per week
This just takes 3 sections and goes into greater detail on content/features.
No attempt is made to attache any time scales.
Sections covered are:
| 4 | UK-GAAP Taxonomy and BROs
| 5 | Import - SAPA Initially
| 6 | Accounts Production
E = Exclude from 'To Do' calcs
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
UK-GAAP Taxonomy and BROs
4 |  | Taxonomy DB and associated Admin Utils | 60 |  | 60 | 0 | 28 |  | 28 | 0 |  |  |  | 0 | 88 | 0 | 88 | 0
4.1 |  | Bros system | 72 |  | 60 | 12 | 28 |  | 28 | 0 |  |  |  | 0 | 100 | 0 | 88 | 12 |  | 0.1 | Including SS Export/Import and summing. StartEnd summing to be finalised once Bros have been created.
4.1 | a | Create Bros | 21 |  | 21 | 0 | 90 |  | 28 | 0 |  |  |  | 0 | 111 | 0 | 49 | 0 |  | 0.1 | Including Bros Tree
| b | Restructure with pseudo CoA |  |  |  |  | 10 |  | 2 | [10 empty] | 0.1 | De-constructed and am now re-constructing. As part of this will put in a CoA feature
4.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 160 | 0 | 141 | 19 | 163 | 0 | 86 | 7 | 0 | 0 | 0 | 0 | 313 | 0 | 225 | 26
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Import - SAPA Initially
5 |  | SAPA export format | 2 |  | 1 | 1 | 14 |  | 10 | 4 |  |  |  | 0 | 16 | 0 | 11 | 5 |  |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
5.1 |  | Importing into Braiins | 28 |  | 21 | 7 | 14 |  | 2 | 12 |  |  |  | 0 | 42 | 0 | 23 | 19 |  |  | Including mapping
5.2 |  | Checking and correcting import data | 28 |  |  | 28 | 7 |  |  | 7 |  |  |  | 0 | 35 | 0 | 0 | 35 |  |  | General checking system to be used by BDT input/edit too
5.3 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 65 | 0 | 22 | 43 | 42 | 0 | 12 | 30 | 0 | 0 | 0 | 0 | 107 | 0 | 34 | 73
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Accounts Production
6 |  | Report Generator | 84 |  | 60 | 24 |  |  |  | 0 |  |  |  | 0 | 84 | 0 | 60 | 24
6.1 | a | Initial formats | 7 |  | 4 | 0 | 120 |  |  | 0 |  |  |  | 0 | 127 | 0 | 4 | 0 |  | 0.1 | Covers bulk of formats but in a fixed style. Recreating UK GAAP taxonomy straight-forward. Though may leave out truly obscure reports. If ability to do things such as Restated and Discontinued Acquired is time consuming that would look to leave them out
| b | Later formats | [17 empty] | 0.2 | Put in anything left out from above e.g. Restated, Discontinued/Acquired, Consolidations
| c | Styles options | [17 empty] | 0.3 | Provide update which gives user control over layout e.g. number of columns, fonts, point size and colours
| d | Graphics | [17 empty] | 2.n | Put in the pretty pictures
6.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 14 |  |  | 14 |  |  |  | 0 | 21 | 0 | 0 | 21
|  |  | 98 | 0 | 64 | 31 | 134 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 232 | 0 | 64 | 45
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
BDT - Braiins DeskTop
7 |  | Initial framework up incl Close | 7 |  | 7 | 0 |  |  |  | 0 |  |  |  | 0 | 7 | 0 | 7 | 0 | 2011-02-27 | 0.1
7.01 |  | Actions: Logout | 0.2 |  | 0.2 | 0 |  |  |  | 0 |  |  |  | 0 | 0.2 | 0 | 0.2 | 0 | 2012-01-01 | 0.1
7.02 |  | Actions: Fullscreen | 0.5 | -0.4 | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.5 | -0.4 | 0.1 | 0 | 2012-01-01 | 0.1 | Done simply via a hint to press F11
7.03 |  | Actions: Minimise all open windows | 0.1 |  | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.1 | 0 | 0.1 | 0 |  | 0.1
7.1 |  | Current Entity: Enter or Edit Data | 56 |  |  | 56 | 14 |  | 1 | 13 |  |  |  | 0 | 70 | 0 | 1 | 69 |  | 0.2 | Time to do this will depend a lot on how many and how complex the input screens are.
7.11 |  | Current Entity: Trial Balance | 14 |  |  | 14 | 2 |  | 1 | 1 |  |  |  | 0 | 16 | 0 | 1 | 15 |  | 0.1 | Includes learning time on chosen report producing grid including printing and pdf etc output.
7.12 |  | Current Entity: Data Trail | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  | 0.1 | Similar to current Utils Data Dump in the BDT environment
7.13 |  | Current Entity: Generate Accounts | 7 |  |  | 7 | 2 |  |  | 2 |  |  |  | 0 | 9 | 0 | 0 | 9 |  | 0.1 | Desktop integration of Accounts Production task above
7.14 |  | Current Entity: Download Accounts | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Exactly how still to be decided.
7.15 |  | Current Entity: Upload Data | 4 |  |  | 4 | 2 |  |  | 2 |  |  |  | 0 | 6 | 0 | 0 | 6 |  | 0.1 | Desktop integration of Import task above
7.16 |  | Current Entity: Set Current Year | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | 0.1 | When credits are used up i.e. charged
7.2 |  | Entities: Change Entity | 4 |  |  | 4 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 4 |  | 0.1 | Envisage a searchable table.
7.21 |  | Entities: New Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Form but have to check for unique ref, name and CH #
7.22 |  | Entities: Edit, Reset, Delete Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Administrator permissions required for Reset and Delete.
7.23 |  | Entities: Entities List | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Similar to the Change Entity table but with report options.
7.3 | E | Interaction: Messages | 14 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 15 | 0 | 0 | 0
7.31 | E | Interaction: Support | 2 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0 |  |  | Based on task 7.30
7.32 | E | Interaction: Documentation | 4 |  |  | 0 | 14 |  |  | 0 |  |  |  | 0 | 18 | 0 | 0 | 0 |  |  | Initial version only
7.4 |  | Preferences: Headings | 8 |  | 6 | 2 | 1 |  |  | 1 |  |  |  | 0 | 9 | 0 | 6 | 3 |  |  | Most of the time was choosing and learning tools time.
7.41 |  | Preferences: Layout Options | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6
7.5 |  | Admin: Agent Details (Account) | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
7.51 |  | Admin: Administrator | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Change administrator
7.52 |  | Admin: Staff | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Add/Edit in two tabs
7.53 |  | Admin: Credits | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10 |  |  | Includes payment processing interaction
7.54 |  | Admin: Download Export Format | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  |  | Charles' work for this is in task 7.2
7.55 |  | Admin: Admin Reports | 7 |  |  | 7 | 1 |  |  | 1 |  |  |  | 0 | 8 | 0 | 0 | 8 |  |  | Audit Trail + ?
7.6 |  | jDesktop tidying up | 10 |  |  | 10 |  |  |  | 0 |  |  |  | 0 | 10 | 0 | 0 | 10
7.61 |  | Misc | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10
|  |  | 177.8 | -0.4 | 13.4 | 144 | 50 | 0 | 2 | 32 | 0 | 0 | 0 | 0 | 227.8 | -0.4 | 15.4 | 176