## Dev
Braiins Development Schedule |  |  |  |  | All times in days | [12 empty] | Revised: | 2012-01-01 |  | Date of last addition of tasks or change in the estimated times.
[18 empty] | Last update: | 2012-01-01 |  | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [12 empty] | Start Date: | 2011-02-01 |  | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [12 empty] | Launch Date: | 2013-01-16 16:00 |  | Projected Ready to Launch Date
Postponed to post launch |  |  |  | Done: | Days completed
Could be postponed to post launch if necessary |  |  |  | To Do: | Days remaining to be done | [12 empty] | 1.1667 | 6 |  | Average effective development days per week
E = Exclude from 'To Do' calcs
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Admin Stuff
1 |  | Choose Name and buy domains | 1 |  | 1 | 0 | 2 |  | 2 | 0 |  |  |  |  | 3 | 0 | 3 | 0 | 2011-02-06 |  | Braiins chosen
1.1 |  | Set up Braiins Ltd UK |  |  |  | 0 | 2 |  | 2 | 0 |  |  |  |  | 2 | 0 | 2 | 0
1.2 |  | Sort out ElanElan or other IBC | 2 |  | 1 | 1 |  |  |  | 0 |  |  |  |  | 2 | 0 | 1 | 1
1.3 |  | Accounting, VAT, legal, banking etc admin stuff |  |  |  | 0 | 5 |  |  | 5 |  |  |  |  | 5 | 0 | 0 | 5
1.4 |  | HMRC Registered |  |  |  | 0 | 2 |  |  | 2 |  |  |  |  | 2 | 0 | 0 | 2
1.5 |  | Other? | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  |  | 3 | 0 | 0 | 3
|  |  | 4 | 0 | 2 | 2 | 13 | 0 | 4 | 9 | 0 | 0 | 0 | 0 | 17 | 0 | 6 | 11
Project
2 |  | Initial Plans | 2 |  | 2 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 3 | 0 | 3 | 0 | 2011-02-03 |  | Main site plus Braiins Desktop
2.1 |  | Tools Selection | 8 |  | 6 | 2 |  |  |  | 0 |  |  |  | 0 | 8 | 0 | 6 | 2 |  |  | html 5, JavaScript, PHP, MySQL, jQuery, jDesktop, SlickGrid, WordPress, UniServer + various other jQuery plugins
2.2 |  | Initial Database design | 2 |  | 2 | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 2 | 0 | 2011-02-14
2.3 |  | Choose Payment Processing Service(s) | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4
2.3 |  | Choose Hosting | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2
2.4 |  | Research, Thinking, Communicating, Negotiating | 50 |  | 23 | 27 | 120 |  | 60 | 60 |  |  |  | 0 | 170 | 0 | 83 | 87
|  |  | 64 | 0 | 33 | 31 | 125 | 0 | 61 | 64 | 0 | 0 | 0 | 0 | 189 | 0 | 94 | 95
Main Braiins.com Site
3 |  | Initial framework up | 7 |  | 7 | 0 | 1 |  | 1 | 0 |  |  |  | 0 | 8 | 0 | 8 | 0 | 2011-02-14
3.1 |  | Logo, favicon, colours, layout/design | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 9 | 0 | 0 | 9 |  |  | Via Freelancer.com? Use template?
3.2 |  | Home Page | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 9 | 0 | 0 | 9 |  |  | Strap line, copy, images + slide show or video?
3.3 |  | Free Trial | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2 |  |  | Small task as currently envisaged
3.4 |  | Registration | 5 |  | 3 | 2 | 3 |  | 2 | 1 |  |  |  | 0 | 8 | 0 | 5 | 3 |  |  | Terms of Service to be updated once task 3.10 is final. Guarantee to be agreed. Add pw strength check?
3.5 |  | Info: Features & Benefits | 1 |  |  | 1 | 5 |  |  | 5 |  |  |  | 0 | 6 | 0 | 0 | 6 |  |  | Charles to write. Incl BDT images as per current Tari page?
3.6 |  | Info: Prices | 1 |  |  | 1 | 3 |  |  | 3 |  |  |  | 0 | 4 | 0 | 0 | 4 |  |  | Charles to research and write
3.7 |  | Info: FAQs | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Charles to write
3.8 |  | Info: About Us | 2 |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 1 | 2 |  |  | Pic and copy due from Charles
3.9 |  | Info: Policies | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | David to revise with check by Charles
3.1 |  | Info: Terms | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Charles to revise. Legal opinion necessary?
3.11 |  | Sitemap | 1 |  | 1 | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 1 | 0
3.12 |  | Contact Us | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  | 0 | 2 | 0 | 0 | 2
3.13 | E | Change from cookies to local storage use | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
3.14 |  | Add browser version warnings | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
3.15 | E | Add Testimonials page | 3 |  |  | 0 | 3 |  |  | 0 |  |  |  | 0 | 6 | 0 | 0 | 0
3.16 |  | Misc | 3 |  |  | 3 | 3 |  |  | 3 |  |  |  | 0 | 6 | 0 | 0 | 6
|  |  | 37 | 0 | 12 | 20 | 33 | 0 | 3 | 27 | 6 | 0 | 0 | 6 | 76 | 0 | 15 | 53
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
UK-GAAP Taxonomy and BROs
4 |  | Taxonomy DB and associated Admin Utils | 60 |  | 60 | 0 | 28 |  | 28 | 0 |  |  |  | 0 | 88 | 0 | 88 | 0
4.1 |  | Bros system | 72 |  | 60 | 12 | 28 |  | 28 | 0 |  |  |  | 0 | 100 | 0 | 88 | 12 |  |  | Including SS Export/Import and summing. StartEnd summing to be finalised once Bros have been created.
4.1 |  | Create Bros | 21 |  | 21 | 0 | 90 |  | 28 | 62 |  |  |  | 0 | 111 | 0 | 49 | 62 |  |  | Including Bros Tree
4.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 160 | 0 | 141 | 19 | 153 | 0 | 84 | 69 | 0 | 0 | 0 | 0 | 313 | 0 | 225 | 88
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Import - SAPA Initially
5 |  | SAPA export format | 2 |  | 1 | 1 | 14 |  | 10 | 4 |  |  |  | 0 | 16 | 0 | 11 | 5 |  |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
5.1 |  | Importing into Braiins | 28 |  | 21 | 7 | 14 |  | 2 | 12 |  |  |  | 0 | 42 | 0 | 23 | 19 |  |  | Including mapping
5.2 |  | Checking and correcting import data | 28 |  |  | 28 | 7 |  |  | 7 |  |  |  | 0 | 35 | 0 | 0 | 35 |  |  | General checking system to be used by BDT input/edit too
5.3 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 65 | 0 | 22 | 43 | 42 | 0 | 12 | 30 | 0 | 0 | 0 | 0 | 107 | 0 | 34 | 73
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Accounts Production
6 |  | Report Generator | 84 |  | 60 | 24 |  |  |  | 0 |  |  |  | 0 | 84 | 0 | 60 | 24
6.1 |  | Initial formats | 7 |  | 4 | 3 | 120 |  |  | 120 |  |  |  | 0 | 127 | 0 | 4 | 123
6.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 14 |  |  | 14 |  |  |  | 0 | 21 | 0 | 0 | 21
|  |  | 98 | 0 | 64 | 34 | 134 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 232 | 0 | 64 | 168
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
BDT - Braiins DeskTop
7 |  | Initial framework up incl Close | 7 |  | 7 | 0 |  |  |  | 0 |  |  |  | 0 | 7 | 0 | 7 | 0 | 2011-02-27
7.01 |  | Actions: Logout | 0.2 |  | 0.2 | 0 |  |  |  | 0 |  |  |  | 0 | 0.2 | 0 | 0.2 | 0 | 2012-01-01
7.02 |  | Actions: Fullscreen | 0.5 | -0.4 | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.5 | -0.4 | 0.1 | 0 | 2012-01-01 |  | Done simply via a hint to press F11
7.03 |  | Actions: Minimise all open windows | 0.1 |  | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.1 | 0 | 0.1 | 0
7.1 |  | Current Entity: Enter or Edit Data | 56 |  |  | 56 | 14 |  | 1 | 13 |  |  |  | 0 | 70 | 0 | 1 | 69 |  |  | Time to do this will depend a lot on how many and how complex the input screens are.
7.11 |  | Current Entity: Trial Balance | 14 |  |  | 14 | 2 |  | 1 | 1 |  |  |  | 0 | 16 | 0 | 1 | 15 |  |  | Includes learning time on chosen report producing grid including printing and pdf etc output.
7.12 |  | Current Entity: Data Trail | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  |  | Similar to current Utils Data Dump in the BDT environment
7.13 |  | Current Entity: Generate Accounts | 7 |  |  | 7 | 2 |  |  | 2 |  |  |  | 0 | 9 | 0 | 0 | 9 |  |  | Desktop integration of Accounts Production task above
7.14 |  | Current Entity: Download Accounts | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  |  | Exactly how still to be decided.
7.15 |  | Current Entity: Upload Data | 4 |  |  | 4 | 2 |  |  | 2 |  |  |  | 0 | 6 | 0 | 0 | 6 |  |  | Desktop integration of Import task above
7.16 |  | Current Entity: Set Current Year | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | When credits are used up i.e. charged
7.2 |  | Entities: Change Entity | 4 |  |  | 4 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 4 |  |  | Envisage a searchable table.
7.21 |  | Entities: New Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  |  | Form but have to check for unique ref, name and CH #
7.22 |  | Entities: Edit, Reset, Delete Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  |  | Administrator permissions required for Reset and Delete.
7.23 |  | Entities: Entities List | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  |  | Similar to the Change Entity table but with report options.
7.3 | E | Interaction: Messages | 14 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 15 | 0 | 0 | 0
7.31 | E | Interaction: Support | 2 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0 |  |  | Based on task 7.30
7.32 | E | Interaction: Documentation | 4 |  |  | 0 | 14 |  |  | 0 |  |  |  | 0 | 18 | 0 | 0 | 0 |  |  | Initial version only
7.4 |  | Preferences: Headings | 8 |  | 6 | 2 | 1 |  |  | 1 |  |  |  | 0 | 9 | 0 | 6 | 3 |  |  | Most of the time was choosing and learning tools time.
7.41 |  | Preferences: Layout Options | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6
7.5 |  | Admin: Agent Details (Account) | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
7.51 |  | Admin: Administrator | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Change administrator
7.52 |  | Admin: Staff | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Add/Edit in two tabs
7.53 |  | Admin: Credits | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10 |  |  | Includes payment processing interaction
7.54 |  | Admin: Download Export Format | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  |  | Charles' work for this is in task 7.2
7.55 |  | Admin: Admin Reports | 7 |  |  | 7 | 1 |  |  | 1 |  |  |  | 0 | 8 | 0 | 0 | 8 |  |  | Audit Trail + ?
7.6 |  | jDesktop tidying up | 10 |  |  | 10 |  |  |  | 0 |  |  |  | 0 | 10 | 0 | 0 | 10
7.61 |  | Misc | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10
|  |  | 177.8 | -0.4 | 13.4 | 144 | 50 | 0 | 2 | 32 | 0 | 0 | 0 | 0 | 227.8 | -0.4 | 15.4 | 176
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Blog
8 | E | Set it up with logo etc @ blog.braiins.com | 4 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 0
8.1 | E | Enable Braiins Newsletter sign up | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 |  |  | Mostly for mailings about Blog posts. Would also be sent to Braiins site members. Need to avoid duplicates
8.2 | E | Write and post launch blogs | 1 |  |  | 0 | 2 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0
8.3 | E | Write and post blogs post launch |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | Ongoing after launch
|  |  | 7 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
Admin
9 | E | Set up an Admin Desktop @ admin.braiins.com | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 |  |  | Based on BDT
9.1 | E | Edit people esp password | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 |  |  | Based on task 7.52
9.2 | E | Support Message System | 1 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
9.3 | E | Credits Journals | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.4 | E | Report: Agents & Entities | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.5 | E | Report: Credits i.e. Money Stuff | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.6 | E | Report: Site Usage and Tracking Stuff | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
9.7 | E | Housekeeping (End of Day) cron task | 2 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 0
9.8 | E | Down for maintenance page | 1 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 0
|  |  | 11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
Marketing
10 |  | Setup Google Analytics & add code to main pages | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
10.1 |  | Submit to SEs | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
10.2 |  | Issue Press Releases | 1 |  |  | 1 | 2 |  |  | 2 |  |  |  | 0 | 3 | 0 | 0 | 3
10.3 |  | Contact AccMan, AW, AA etc | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1
10.4 | E | More, much more…. | 2 |  |  | 0 | 10 |  |  | 0 |  |  |  | 0 | 12 | 0 | 0 | 0
|  |  | 6 | 0 | 0 | 4 | 12 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 6
Launch Preparation
11 |  | Test and fix, test and fix incl cross browser issues | 14 |  |  | 14 | 7 |  |  | 7 |  |  |  | 0 | 21 | 0 | 0 | 21
11.1 |  | Get HMRC approval | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4
11.2 |  | Set up deployment server | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  |  | Incl gzip
11.3 |  | Tidy & minimise JS, CSS, HTML + optimise | 3 |  |  | 3 |  |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 3
11.4 |  | Get SSL certificate and get SSL working | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
11.5 |  | Remove authorisation login |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 2 minutes!
11.6 |  | Finalise payment processing | 2 |  |  | 2 | 2 |  |  | 2 |  |  |  | 0 | 4 | 0 | 0 | 4
11.7 |  | Misc | 7 |  |  | 7 | 5 |  |  | 5 |  |  |  | 0 | 12 | 0 | 0 | 12
|  |  | 31 | 0 | 0 | 31 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 48
12 |  | Unallocated Braiins Days | 0 |  | 0 | 0 | 209.55 |  | 121.1429 | 88.4072 |  |  |  | 0 | 209.55 | 0 | 121.1429 | 88.4072 |  |  | 'Done' days calculated as difference between Available and Total days below.
|  | Totals and Ready to LAUNCH Day | 660.8 | -0.4 | 287.4 | 328 | 582 | 0 | 166 | 472.4072 | 6 | 0 | 0 | 6 | 1458.35 | -0.4 | 574.5429 | 806.4072 | 2013-01-16 16:00 |  | Based on D "To Do" days
|  | Total days incl Var, % done | 660.4 | 43.52% |  |  | 582 | 28.52% |  |  | 6 | 0% |  | 0 | 1457.95 | 39.41% |  |  | 2013-07-04 03:24 |  | Based on C "To Do" days
|  | Available days (effective days) |  |  | 287.1429 |  |  |  | 287.1429 |  |  |  |  | -6
| E | Excluded Task Days |  |  | 45 |  |  |  | 32 |  |  |  |  | 0 |  |  | 77
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Post Launch
13 |  | Add Testimonials page | [15 empty] | 0
13.1 |  | Write and post blogs post launch | [15 empty] | 0
13.2 |  | Down for maintenance page | [15 empty] | 0
13.3 |  | Admin site
13.4 |  | Video on HP | [15 empty] | 0
13.5 |  | Ongoing…..
Notes:
Document Issue History | [18 empty] | Projected Ready for Launch Date at time of issue
09 Mar 11 First issue | [18 empty] | 2011-10-01 |  | Dreaming!
02 Jan 12 | [18 empty] | 2013-07-04 |  | Need to improve on this
Formulas:
Est/Act Date = T2+[To Do]*S6-1
Est/Act Date = T2+[To Do, row above]*S6-1

## Versions
DESIGN MAXIM | Simply true, truly beautiful
VERSION | SUMMARY
.01 | Simple SAPA XBRL bolt on v1
Covers bulk of formats but in a fixed style. Recreating UK GAAP taxonomy straight-forward. Cover most common and easy.
0.2 | Simple SAPA XBRL bolt on v2
Put in any formats left out from above e.g. Restated, Discontinued/Acquired, Consolidations
1.0 | Equates to SFS
Control layout of formats: Include/exclude, fonts, columns
2.0 | Self contained AP system
Manually enter and edit data.
3.0 | Getting fancy
Insert graphics?
Insert Objects?
4.0 | New Taxonomy 1
Charities
5.0 | New Taxonomy 2
UK-IFRS
N.n | Ultimate
Objective is to eliminate as many tasks as possible between Entity source and AP output
e.g. Data re-entry, duplicating SSs. Put as much pwer as possible within the BRAIINs itself
So it become it what its name says.
Provide ability to directly import from all major GL systems
XBRL In.
Cover all English language taxonomies.

## Details
Braiins Development Schedule |  |  |  |  | All times in days | [12 empty] | Revised: | 2012-01-01 |  | Date of last addition of tasks or change in the estimated times.
[18 empty] | Last update: | 2012-01-01 |  | Date of last "done" update.
Colour Codes |  |  |  | Est: | Estimated days | [12 empty] | Start Date: | 2011-02-01 |  | Development start date
Completed |  |  |  | Var: | Variation from original estimate | [12 empty] | Launch Date: | #REF! |  | Projected Ready to Launch Date
Postponed to post launch |  |  |  | Done: | Days completed
Could be postponed to post launch if necessary |  |  |  | To Do: | Days remaining to be done | [12 empty] | 1.1667 | 6 |  | Average effective development days per week
This just takes 3 sections and goes into greater detail on content/features.
No attempt is made to attache any time scales.
Sections covered are:
| 4 | UK-GAAP Taxonomy and BROs
| 5 | Import - SAPA Initially
| 6 | Accounts Production
E = Exclude from 'To Do' calcs
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
UK-GAAP Taxonomy and BROs
4 |  | Taxonomy DB and associated Admin Utils | 60 |  | 60 | 0 | 28 |  | 28 | 0 |  |  |  | 0 | 88 | 0 | 88 | 0
4.1 |  | Bros system | 72 |  | 60 | 12 | 28 |  | 28 | 0 |  |  |  | 0 | 100 | 0 | 88 | 12 |  | 0.1 | Including SS Export/Import and summing. StartEnd summing to be finalised once Bros have been created.
4.1 | a | Create Bros | 21 |  | 21 | 0 | 90 |  | 28 | 0 |  |  |  | 0 | 111 | 0 | 49 | 0 |  | 0.1 | Including Bros Tree
| b | Restructure with pseudo CoA |  |  |  |  | 10 |  | 2 | [10 empty] | 0.1 | De-constructed and am now re-constructing. As part of this will put in a CoA feature
4.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 160 | 0 | 141 | 19 | 163 | 0 | 86 | 7 | 0 | 0 | 0 | 0 | 313 | 0 | 225 | 26
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Import - SAPA Initially
5 |  | SAPA export format | 2 |  | 1 | 1 | 14 |  | 10 | 4 |  |  |  | 0 | 16 | 0 | 11 | 5 |  |  | Charles to nominate what the formats need and to write the SAPA export format accordingly
5.1 |  | Importing into Braiins | 28 |  | 21 | 7 | 14 |  | 2 | 12 |  |  |  | 0 | 42 | 0 | 23 | 19 |  |  | Including mapping
5.2 |  | Checking and correcting import data | 28 |  |  | 28 | 7 |  |  | 7 |  |  |  | 0 | 35 | 0 | 0 | 35 |  |  | General checking system to be used by BDT input/edit too
5.3 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 7 |  |  | 7 |  |  |  | 0 | 14 | 0 | 0 | 14
|  |  | 65 | 0 | 22 | 43 | 42 | 0 | 12 | 30 | 0 | 0 | 0 | 0 | 107 | 0 | 34 | 73
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
Accounts Production
6 |  | Report Generator | 84 |  | 60 | 24 |  |  |  | 0 |  |  |  | 0 | 84 | 0 | 60 | 24
6.1 | a | Initial formats | 7 |  | 4 | 0 | 120 |  |  | 0 |  |  |  | 0 | 127 | 0 | 4 | 0 |  | 0.1 | Covers bulk of formats but in a fixed style. Recreating UK GAAP taxonomy straight-forward. Though may leave out truly obscure reports. If ability to do things such as Restated and Discontinued Acquired is time consuming that would look to leave them out
| b | Later formats | [17 empty] | 0.2 | Put in anything left out from above e.g. Restated, Discontinued/Acquired, Consolidations
| c | Styles options | [17 empty] | 0.3 | Provide update which gives user control over layout e.g. number of columns, fonts, point size and colours
| d | Graphics | [17 empty] | 2.n | Put in the pretty pictures
6.2 |  | Maintenance, handling issues arising | 7 |  |  | 7 | 14 |  |  | 14 |  |  |  | 0 | 21 | 0 | 0 | 21
|  |  | 98 | 0 | 64 | 31 | 134 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 232 | 0 | 64 | 45
Ref | E | Task | David |  |  |  | Charles |  |  |  | Others |  |  |  | Total |  |  |  | Est/Act Date | Product Version | Comments
|  |  | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do | Est. | Var | Done | To Do
BDT - Braiins DeskTop
7 |  | Initial framework up incl Close | 7 |  | 7 | 0 |  |  |  | 0 |  |  |  | 0 | 7 | 0 | 7 | 0 | 2011-02-27 | 0.1
7.01 |  | Actions: Logout | 0.2 |  | 0.2 | 0 |  |  |  | 0 |  |  |  | 0 | 0.2 | 0 | 0.2 | 0 | 2012-01-01 | 0.1
7.02 |  | Actions: Fullscreen | 0.5 | -0.4 | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.5 | -0.4 | 0.1 | 0 | 2012-01-01 | 0.1 | Done simply via a hint to press F11
7.03 |  | Actions: Minimise all open windows | 0.1 |  | 0.1 | 0 |  |  |  | 0 |  |  |  | 0 | 0.1 | 0 | 0.1 | 0 |  | 0.1
7.1 |  | Current Entity: Enter or Edit Data | 56 |  |  | 56 | 14 |  | 1 | 13 |  |  |  | 0 | 70 | 0 | 1 | 69 |  | 0.2 | Time to do this will depend a lot on how many and how complex the input screens are.
7.11 |  | Current Entity: Trial Balance | 14 |  |  | 14 | 2 |  | 1 | 1 |  |  |  | 0 | 16 | 0 | 1 | 15 |  | 0.1 | Includes learning time on chosen report producing grid including printing and pdf etc output.
7.12 |  | Current Entity: Data Trail | 4 |  |  | 4 | 1 |  |  | 1 |  |  |  | 0 | 5 | 0 | 0 | 5 |  | 0.1 | Similar to current Utils Data Dump in the BDT environment
7.13 |  | Current Entity: Generate Accounts | 7 |  |  | 7 | 2 |  |  | 2 |  |  |  | 0 | 9 | 0 | 0 | 9 |  | 0.1 | Desktop integration of Accounts Production task above
7.14 |  | Current Entity: Download Accounts | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Exactly how still to be decided.
7.15 |  | Current Entity: Upload Data | 4 |  |  | 4 | 2 |  |  | 2 |  |  |  | 0 | 6 | 0 | 0 | 6 |  | 0.1 | Desktop integration of Import task above
7.16 |  | Current Entity: Set Current Year | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  | 0.1 | When credits are used up i.e. charged
7.2 |  | Entities: Change Entity | 4 |  |  | 4 |  |  |  | 0 |  |  |  | 0 | 4 | 0 | 0 | 4 |  | 0.1 | Envisage a searchable table.
7.21 |  | Entities: New Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Form but have to check for unique ref, name and CH #
7.22 |  | Entities: Edit, Reset, Delete Entity | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Administrator permissions required for Reset and Delete.
7.23 |  | Entities: Entities List | 2 |  |  | 2 |  |  |  | 0 |  |  |  | 0 | 2 | 0 | 0 | 2 |  | 0.1 | Similar to the Change Entity table but with report options.
7.3 | E | Interaction: Messages | 14 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 15 | 0 | 0 | 0
7.31 | E | Interaction: Support | 2 |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 3 | 0 | 0 | 0 |  |  | Based on task 7.30
7.32 | E | Interaction: Documentation | 4 |  |  | 0 | 14 |  |  | 0 |  |  |  | 0 | 18 | 0 | 0 | 0 |  |  | Initial version only
7.4 |  | Preferences: Headings | 8 |  | 6 | 2 | 1 |  |  | 1 |  |  |  | 0 | 9 | 0 | 6 | 3 |  |  | Most of the time was choosing and learning tools time.
7.41 |  | Preferences: Layout Options | 5 |  |  | 5 | 1 |  |  | 1 |  |  |  | 0 | 6 | 0 | 0 | 6
7.5 |  | Admin: Agent Details (Account) | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3
7.51 |  | Admin: Administrator | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Change administrator
7.52 |  | Admin: Staff | 2 |  |  | 2 | 1 |  |  | 1 |  |  |  | 0 | 3 | 0 | 0 | 3 |  |  | Add/Edit in two tabs
7.53 |  | Admin: Credits | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10 |  |  | Includes payment processing interaction
7.54 |  | Admin: Download Export Format | 1 |  |  | 1 |  |  |  | 0 |  |  |  | 0 | 1 | 0 | 0 | 1 |  |  | Charles' work for this is in task 7.2
7.55 |  | Admin: Admin Reports | 7 |  |  | 7 | 1 |  |  | 1 |  |  |  | 0 | 8 | 0 | 0 | 8 |  |  | Audit Trail + ?
7.6 |  | jDesktop tidying up | 10 |  |  | 10 |  |  |  | 0 |  |  |  | 0 | 10 | 0 | 0 | 10
7.61 |  | Misc | 7 |  |  | 7 | 3 |  |  | 3 |  |  |  | 0 | 10 | 0 | 0 | 10
|  |  | 177.8 | -0.4 | 13.4 | 144 | 50 | 0 | 2 | 32 | 0 | 0 | 0 | 0 | 227.8 | -0.4 | 15.4 | 176